## PcdReport.asp
PCD Report
PCD | Date | Current Status | Closed By | Date Closed | Approved By | Date Approved | Rework By | Date Sent for Rework | Revised By | Dept | Originator | Subject | Due Date | Contract(s) / Purchase Order(s) | Action Responsible Person(s) | Program Recipients | Program(s) | Program to use in PCD number | Additional Recipient(s) | Work Package | Action / Comments | Reference | Closure Comments | Rework Comments | Attachments
16-ARCI FY17 TI16 Production-LMDM-PCD00001 | 12/8/2016 | Approved |  |  | William Jones | 12/8/2016 |  |  | 16-ARCI FY17 TI16 Production-LMDM-PCD00001A | M7F4 | Jones, William | Program Control Directive for FY17 TI16 SSBN (3P) System & Pre-Cable kits. |  | N00024-15-C-6222 (FY17 TI16 Production) | Nider, Kenneth (Ken) - Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Vest, Rita , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Colleyacme, Mark , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 12/05/2016 The purpose of this PCD is to serve as an Initial WAD, authorizing the procurement, manufacturing and labor efforts for FY17 SSBN TI02 to TI16 3P System Upgrade. The Period of Performance (POP) for this effort shall be from Oct 2016 thru March 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Man Work Number Description Qty RDD Package Clin 0215AA N148190-1 Ph2 TI02 to TI16 1 07/01/2017 1MFY175AAMMA Man Hdw 1MFY175AACIK Clw Hdw, Touch 1MFY175AACLO Clw LOE Labor 11/15/2017 1MFY175AAPMA Prgy Hdw 11/15/2017 1MFY175AAPGD GD-AIS Hdw Note: Hardware required for manufacturing are due 07/01/2017, Units required for System Demo are required 1/15/2017. Clin 0215AB N148009-1 TI16 Pre-Cable 1 06/01/2017 1MFY175ABCIK Clw Hdw, Touch N165806-1 COTS PCK 1 06/01/2017 1MFY175ABCLO Clw LOE Labor Contract Work Package Recurring Support System Work Package Clin Status Man Configuration Mgt. 1MFY175AAMCM 0215AA Open for Charges Man Production Control 1MFY175AAMPC 0215AA Open for Charges Man Software Control 1MFY175AAMSC 0215AA Open for Charges Man Manufacturing Eng. 1MFY175AAMME 0215AA Open for Charges Man System Test 1MFY175AAMSY 0215AA Open for Charges Man GFE Handling/Teardown/Reuse 1MFY175AAMGF 0215AA Open for Charges Man Touch Labor 1MFY175AAMTL 0215AA Open for Charges | N00025-15-C-6222 Mod P00010 dated 8 November 2016 |  |  | FY17 SSBN Production Budgets (1MFY17) Initial PCD.xlsx
16-ARCI FY17 TI16 Production-LMDM-PCD00001A | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive for FY17 TI16 SSBN (3P) System, Pre-Cable and Spares kits. |  | N00024-15-C-6222 (FY17 TI16 Production) | Nider, Kenneth (Ken) - Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 3/22/2017 The purpose of this PCD is to serve as an initial WAD, authorizing the procurement, manufacturing and labor efforts for FY17 SSBN TI02 to TI16 3P Spares Kit. The Period of Performance (POP) for this effort shall be from March 2017 thru March 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Man Work Number Description Qty RDD Package Clin 0215AC N165076-1 Spares kit 1 07/01/2017 1MFY175ACMCK Man Hdw 1MFY175ACCSK Clw Hdw/Touch Lbr 1MFY175ACCNL Clw Non Touch Lbr 1MFY175ACCLO Clw LOE Lbr 1MFY175ACPSK Prgy Hdw ____________________________________________________________________________ 12/05/2016 The purpose of this PCD is to serve as an Initial WAD, authorizing the procurement, manufacturing and labor efforts for FY17 SSBN TI02 to TI16 3P System Upgrade. The Period of Performance (POP) for this effort shall be from Oct 2016 thru March 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Man Work Number Description Qty RDD Package Clin 0215AA N148190-1 Ph2 TI02 to TI16 1 07/01/2017 1MFY175AAMMA Man Hdw 1MFY175AACIK Clw Hdw, Touch 1MFY175AACLO Clw LOE Labor 11/15/2017 1MFY175AAPMA Prgy Hdw 11/15/2017 1MFY175AAPGD GD-AIS Hdw Note: Hardware required for manufacturing are due 07/01/2017, Units required for System Demo are required 1/15/2017. Clin 0215AB N148009-1 TI16 Pre-Cable 1 06/01/2017 1MFY175ABCIK Clw Hdw, Touch N165806-1 COTS PCK 1 06/01/2017 1MFY175ABCLO Clw LOE Labor Contract Work Package Recurring Support System Work Package Clin Status Man Configuration Mgt. 1MFY175AAMCM 0215AA Open for Charges Man Production Control 1MFY175AAMPC 0215AA Open for Charges Man Software Control 1MFY175AAMSC 0215AA Open for Charges Man Manufacturing Eng. 1MFY175AAMME 0215AA Open for Charges Man System Test 1MFY175AAMSY 0215AA Open for Charges Man GFE Handling/Teardown/Reuse 1MFY175AAMGF 0215AA Open for Charges Man Touch Labor 1MFY175AAMTL 0215AA Open for Charges | N00025-15-C-6222 Mod P00010 dated 8 November 2016 and P00014 dated 2 March 2017. Reference PCD 16-ARCI FY17 TI16 Production-LMDM-PCD0001 dated 12/1/2016. |  |  | FY17 SSBN Production Budgets (1MFY17) Initial PCD.xlsx , ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
16-ARCI FY17 TI16 Production-LMDM-PCD00002 | 12/8/2016 | Approved |  |  | William Jones | 12/8/2016 |  |  | Current | M7F4 | Jones, William | Program Control Directive for FY17 TI16 SSBN (5P) System & Pre-Cable kits. |  | N00024-15-C-6222 (FY17 TI16 Production) | Nider, Kenneth (Ken) - Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Vest, Rita , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Colleyacme, Mark , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 12/05/2016 The purpose of this PCD is to serve as an Initial WAD, authorizing the procurement, manufacturing and labor efforts for FY17 SSBN TI02 to TI16 (5P) System Upgrade. The Period of Performance (POP) for this effort shall be from Oct 2016 thru July 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Man Work Number Description Qty RDD Package Clin 0215AG N148190-1 Ph2 TI02 to TI16 1 10/01/2017 1MFY175AGMMA Man Hdw 1MFY175AGCIK Clw Hdw, Touch 1MFY175AGCLO Clw LOE Labor 01/15/2018 1MFY175AGPMA Prgy Hdw 01/15/2018 1MFY175AGPGD GD-AIS Hdw Note: Hardware required for manufacturing are due 10/01/2017, Units required for System Demo are required 1/15/2018. Clin 0215AH N148009-1 TI16 Pre-Cable 1 11/20/2017 1MFY175AHCIK Clw Hdw, Touch N165806-1 COTS PCK 1 11/20/2017 1MFY175AHCLO Clw LOE Labor Contract Work Package Recurring Support System Work Package Clin Status Man Configuration Mgt. 1MFY175AGMCM 0215AG Open for Charges Man Production Control 1MFY175AGMPC 0215AG Open for Charges Man Software Control 1MFY175AGMSC 0215AG Open for Charges Man Manufacturing Eng. 1MFY175AGMME 0215AG Open for Charges Man System Test 1MFY175AGMSY 0215AG Open for Charges Man GFE Handling/Teardown/Reuse 1MFY175AGMGF 0215AG Open for Charges Man Touch Labor 1MFY175AGMTL 0215AG Open for Charges | N00025-15-C-6222 Mod P00010 dated 8 November 2016. |  |  | FY17 SSBN Production Budgets (1MFY17) Initial PCD.xlsx
16-ARCI FY17 TI16 Production-LMDM-PCD00003 | 12/8/2016 | Approved |  |  | William Jones | 12/8/2016 |  |  | Current | M7F4 | Jones, William | Program Control Directive for FY17 TI16 SSBN (4L) System & Pre-Cable kits. |  | N00024-15-C-6222 (FY17 TI16 Production) | Nider, Kenneth (Ken) - Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Vest, Rita , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Colleyacme, Mark , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 12/05/2016 The purpose of this PCD is to serve as an Initial WAD, authorizing the procurement, manufacturing and labor efforts for FY17 SSBN TI02 to TI16 4L System Upgrade. The Period of Performance (POP) for this effort shall be from Oct 2016 thru December 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Man Work Number Description Qty RDD Package Clin 0215AD N148190-2 Ph2 TI02 to TI16 1 01/01/2018 1MFY175ADMMA Man Hdw 1MFY175ADCIK Clw Hdw, Touch 1MFY175ADCLO Clw LOE Labor 04/15/2018 1MFY175ADPMA Prgy Hdw 04/15/2018 1MFY175ADPGD GD-AIS Hdw Note: Hardware required for manufacturing are due 01/01/2018, Units required for System Demo are required 04/15/2018. Clin 0215AE N148009-1 TI16 Pre-Cable 1 11/09/2017 1MFY175AECIK Clw Hdw, Touch N165806-1 COTS PCK 1 11/09/2017 1MFY175AECLO Clw LOE Labor Contract Work Package Recurring Support System Work Package Clin Status Man Configuration Mgt. 1MFY175ADMCM 0215AD Open for Charges Man Production Control 1MFY175ADMPC 0215AD Open for Charges Man Software Control 1MFY175ADMSC 0215AD Open for Charges Man Manufacturing Eng. 1MFY175ADMME 0215AD Open for Charges Man System Test 1MFY175ADMSY 0215AD Open for Charges Man GFE Handling/Teardown/Reuse 1MFY175ADMGF 0215AD Open for Charges Man Touch Labor 1MFY175ADMTL 0215AD Open for Charges | N00025-15-C-6222 Mod P00010 dated 8 November 2016 |  |  | FY17 SSBN Production Budgets (1MFY17) Initial PCD.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00001 | 1/19/2017 | Approved |  |  | Joseph Fanto | 1/19/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00001A | M7F5 | Lemus, Nimssi | Program Control Directive to order LVA 790 ABF Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Vest, Rita , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Colleyacme, Mark , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comment section of this PCD. | 01/17/2017- The purpose of this PCD authorizes the procurement, and labor efforts for LVA 790 ABF Delta Hardware kits. The ABF delta hardware kits are being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESC3H380 Clw Hdw 1M17ESC4H380 Clw Labor 1M17ESM3G379 Man Hdw 1MFY167ANPGM Man Labor | Email Note: From N. Lemus dated Jan 16 2017. |  |  | LVA 790 Additional ABF Delta_HW List_790_v02.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00001A | 2/21/2017 | Approved |  |  | Joseph Fanto | 2/21/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00001B | M7F5 | Lemus, Nimssi | Program Control Directive to order LVA 790 ABF Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Duggins, April (April) - Burcin, William (Billy) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work Package Remarks 1M17ESC3H380 Clw Hdw 1M17ESC4H380 Clw Labor 1M17ESM3G379 Man Hdw 1MFY167ANPGM Man Labor | Revision A: 1)PC is directed to delete the following PRs: 4300486304 4300486305 4300486307 2)PC is directed to issue P2P PRs to procure the following instead: PART NUMEBR QTY TFT TI14-S01-2 SIM TO SERVER 2 TFT TI14-S43-3 SIM TO SERVER 1 Direct PRs to April Galbraith (Duggins). ======================================================================== 01/17/2017- The purpose of this PCD authorizes the procurement, and labor efforts for LVA 790 ABF Delta Hardware kits. The ABF delta hardware kits are being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESC3H380 Clw Hdw 1M17ESC4H380 Clw Labor 1M17ESM3G379 Man Hdw 1MFY167ANPGM Man Labor | Email Note: From N. Lemus dated Jan 16 2017. |  |  | LVA 790 Additional ABF Delta_HW List_790_v02.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00001B | 3/29/2017 | Approved |  |  | Stephen Zajkowski | 3/29/2017 |  |  | Current | M7F5 | Lemus, Nimssi | Program Control Directive to order LVA 790 ABF Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Duggins, April (April) - Burcin, William (Billy) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work Package Remarks 1M17ESC3H380 Clw Hdw 1M17ESC4H380 Clw Labor 1M17ESM3G379 Man Hdw 1MFY167ANPGM Man Labor | Revision B: PC is directed to delete PR# 4300486247 for PN N135652. This part is now obsolete and no longer procurable. PC is directed to issue a PR for the following to replace the obsolete part: PN DESCRIPTION QTY N150128 HP A5820-24XG-SFP+ SWITCH 17 See line 5 of attached v03 spreadsheet for changes. =========================================================================== Revision A: 1)PC is directed to delete the following PRs: 4300486304 4300486305 4300486307 2)PC is directed to issue P2P PRs to procure the following instead: PART NUMEBR QTY TFT TI14-S01-2 SIM TO SERVER 2 TFT TI14-S43-3 SIM TO SERVER 1 Direct PRs to April Galbraith (Duggins). ======================================================================== 01/17/2017- The purpose of this PCD authorizes the procurement, and labor efforts for LVA 790 ABF Delta Hardware kits. The ABF delta hardware kits are being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESC3H380 Clw Hdw 1M17ESC4H380 Clw Labor 1M17ESM3G379 Man Hdw 1MFY167ANPGM Man Labor | Email Note: From N. Lemus dated Jan 16 2017. |  | This part is now obsolete and no longer procurable. change no to now | LVA 790 Additional ABF Delta_HW_List_790_v03.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00002 | 1/26/2017 | Approved |  |  | Joey Eubank | 1/26/2017 |  |  | Current | M7F5 | Eubank, Joey | Program Control Directive to Order LASC OBE Materials for SSNs 798-801 | 12/31/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Mullins, Jeremiyah (Jeremiyah) - Lonnquest, David (David) - Johns, Christopher (Chris) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Vest, Rita , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Colleyacme, Mark , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production | Lemus, Nimssi (Nimssi) | Work packages are provided in the attachment to this PCD. | 01/26/2017- The purpose of this PCD is to serve as an initial WAD (covered by Z-2017-FEA-5), authorizing the labor efforts and materails costs for the procurement of materials needed on 798-801 LASC: 77C962400G1 ASSY, LAB OBE COMPLETE SHIP SET (42 OBE'S) The period of performance shall be January 2017- December 2017. The current Virginia New Construction Schedule A dates for delivery of LASC OBEs are: SSN 798 05/01/2018 SSN 799 08/24/2018 SSN 800 02/01/2019 SSN 801 07/23/2019 | Z-2017-FEA-5 |  |  | ARCI ES 6222 iWAD 798-801.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00003 | 2/2/2017 | Approved |  |  | William Jones | 2/2/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive authorizing Proposal effort for SSN 798 thru 801 Spares Hardware. |  | N00024-15-C-6222 (FY17 TI16 Production) | DeRancy, Daniel (Daniel) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | 1MT16A8901PP Proposal Prep for SSN 798 thru SSN 801 Spares. | 2/2/2017 The purpose of this PCD is to serve as an initial WAD (covered by FEA 2017-FEA-6), authorizing the labor effort costs for the proposal of materials and labor needed on the SSN 798 thru SSN 801 Spares. The period of performance shall be January 9, 2017 - December 2017. Please note the Charge number is valid as of January 9 2017. Note: Per PPMD 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out the Open/Close Charge ID Macro contained in folder 40 on the EVM portal. | Email Note: From Dan Derancy dated 2 February 2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00004 | 2/9/2017 | Approved |  |  | Joey Eubank | 2/9/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive for FY17 TI16 SSN 779 Pre-Cable kit. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | 1MFY17779PCK Shall be used for this effort. | 12/05/2016 The purpose of this PCD is to serve as an Initial WAD, (covered by FEA 2017-5), authorizing the labor efforts and material costs for the procurement of materials needed on 779 PCK. The Period of Performance (POP) for this effort shall be from Feb 2017 thru July 2017. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Estimated Man Work Number Description Qty cost RDD Package N148547-1 Pre-Cable kit 1 $8k 7/1/2017 1MFY17779PCK | FEA Z-2017-FEA-5 ARCI Production Lab Array and SSN 779 PCK.
17-ARCI FY17 TI16 Production-LMDM-PCD00005 | 2/16/2017 | Approved |  |  | William Jones | 2/16/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to order TPS Slides for SSN 772 4135 Unit.. |  | N00024-15-C-6222 (FY17 TI16 Production) | Nider, Kenneth (Ken) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production | Nider, Kenneth (Ken) | 1MFY153HBMTL | 2/16/2017 LM Production Control (K. Nider) is authorized/directed to order the below listed TPS Slides for the SSN 772 4135 Unit. Part Number Nomenclature Qty Cost Each Work Package 1507089-P 4135 TPS Slides 2 $1,878.00 1MFY153HBMTL | Email Note: From R Charlsen dated 16 Feb 2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006 | 2/21/2017 | Approved |  |  | Joey Eubank | 2/21/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006A | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006A | 2/22/2017 | Approved |  |  | William Jones | 2/22/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006B | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017 and 2/21/2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006B | 2/23/2017 | Approved |  |  | William Jones | 2/23/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006C | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 2/22/2017 - This PCD revision deletes 3 part numbers and adds a column to the attached file identifying vendor selection. ____________________________________________________________________________ 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017, 2/21/2017 and 2/22/2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006C | 3/1/2017 | Approved |  |  | William Jones | 3/1/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006D | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 3/1/2017 - This PCD revision adds P/N N139490 TI-14-HDD10-1 Qty 96 to the Hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 2/22/2017 - This PCD revision deletes 3 part numbers and adds a column to the attached file identifying vendor selection. ____________________________________________________________________________ 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017, 2/21/2017, 2/22/2017 and 2/28/2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006D | 3/15/2017 | Approved |  |  | William Jones | 3/15/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006E | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 3/15/2017 - This PCD revision updates the TI14-S34-2 (N139625) server to TI14-S34-3 (N147939) on the Hardware List provided as an attachment to this PCD. ____________________________________________________________________________ 3/1/2017 - This PCD revision adds P/N N139490 TI-14-HDD10-1 Qty 96 to the Hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 2/22/2017 - This PCD revision deletes 3 part numbers and adds a column to the attached file identifying vendor selection. ____________________________________________________________________________ 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017, 2/21/2017, 2/22/2017, 2/28/2017, and 3/15/2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006E | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006F | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 3/22/2017 - This PCD removes Part number N135652 (HP A5820 Network Switch from the Bill of Material provided as an attachment to this PCD. LM was informed that this part was no longer available. An alternate part shall be added at a later date. ____________________________________________________________________________ 3/15/2017 - This PCD revision updates the TI14-S34-2 (N139625) server to TI14-S34-3 (N147939) on the Hardware List provided as an attachment to this PCD. ____________________________________________________________________________ 3/1/2017 - This PCD revision adds P/N N139490 TI-14-HDD10-1 Qty 96 to the Hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 2/22/2017 - This PCD revision deletes 3 part numbers and adds a column to the attached file identifying vendor selection. ____________________________________________________________________________ 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017, 2/21/2017, 2/22/2017, 2/28/2017, 3/15/2017 and 3/21/2017. |  |  | LVA 790 Additional ABF Dela_Remaining_HW_List_790_.V7.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00006F | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00006G | M633 | Mullins, Jeremiyah | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 3/22/2017- This PCD adds Janet Myers as an action owner. ____________________________________________________________________________ 3/22/2017 - This PCD removes Part number N135652 (HP A5820 Network Switch from the Bill of Material provided as an attachment to this PCD. LM was informed that this part was no longer available. An alternate part shall be added at a later date. ____________________________________________________________________________ 3/15/2017 - This PCD revision updates the TI14-S34-2 (N139625) server to TI14-S34-3 (N147939) on the Hardware List provided as an attachment to this PCD. ____________________________________________________________________________ 3/1/2017 - This PCD revision adds P/N N139490 TI-14-HDD10-1 Qty 96 to the Hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 2/22/2017 - This PCD revision deletes 3 part numbers and adds a column to the attached file identifying vendor selection. ____________________________________________________________________________ 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ____________________________________________________________________________ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017, 2/21/2017, 2/22/2017, 2/28/2017, 3/15/2017 and 3/21/2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00006G | 4/13/2017 | Approved |  |  | William Jones | 4/13/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to order LVA 790 ABF Remaining Delta Hardware. | 2/1/2017 | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Work package provided in the Action/Comments section of this PCD. | 04/13/2017 This PCD adds the replacement part N150128 HP A5820 Network Switch Qty (35) to the attached file provided as an attachment with this PCD. ___________________________________________________________________________ 3/22/2017- This PCD adds Janet Myers as an action owner. ___________________________________________________________________________ _ 3/22/2017 - This PCD removes Part number N135652 (HP A5820 Network Switch from the Bill of Material provided as an attachment to this PCD. LM was informed that this part was no longer available. An alternate part shall be added at a later date. ___________________________________________________________________________ _ 3/15/2017 - This PCD revision updates the TI14-S34-2 (N139625) server to TI14-S34-3 (N147939) on the Hardware List provided as an attachment to this PCD. ___________________________________________________________________________ _ 3/1/2017 - This PCD revision adds P/N N139490 TI-14-HDD10-1 Qty 96 to the Hardware list provided as an attachment to this PCD. ___________________________________________________________________________ _ 2/22/2017 - This PCD revision deletes 3 part numbers and adds a column to the attached file identifying vendor selection. ___________________________________________________________________________ _ 2/22/2017 - This PCD revision updates/corrects the attached hardware list provided as an attachment to this PCD. ___________________________________________________________________________ _ 02/21/2017- The purpose of this PCD is to authorize/direct LM Manassas operations (J. Mullins) the procurement, and labor efforts to order the additional LVA 790 ABF Delta Hardware. The additional 790 ABF delta hardware is being procured via Engineering Service Task utilizing ODC Funds. The Hardware list shall be provided as an attachment with this PCD. Work packages are provided below. Work Package Remarks 1M17ESM4G379 LVA 790 ABF Delta COTS Labor. 1M17ESM5G379 LVA 790 ABF Delta COTS Additional Hardware | Email Note: From N. Lemus dated 2/20/2017, 2/21/2017, 2/22/2017, 2/28/2017, 3/15/2017, 3/21/2017 and 4/13/2017. |  |  | LVA 790 Additional ABF Dela_Remaining_HW_List_790_.V8.xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00007 | 2/21/2017 | Approved |  |  | William Jones | 2/21/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive for FY17 TI16 SSN 798 Early ASRU Delivery kit N137732-1 |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | 1MT16A0798CW Shall be used for LLEOQ Hardware and Touch Labor for this effort. | 12/05/2016 The purpose of this PCD is to serve as an Initial WAD, (covered by FEA 2017-5), authorizing the labor efforts and material costs for the procurement of materials needed on 798 ASRU Early delivery kit. The Period of Performance (POP) for this effort shall be from Feb 2017 thru September 2019. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Part Work Number Description Qty Package N137732-1 ASRU Early delivery Kit 1 1MT16A0798CW | FEA Z-2017-FEA-5 ARCI Production Lab Array, SSN 779 PCK and SSN 798 Early ASRU delivery kit. Email Note: From J. Eubank dated 20 Feb 2017. |  | fix title
17-ARCI FY17 TI16 Production-LMDM-PCD00008 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Prodgram Control Directive to order Technology Part Task Trainer (TPTT), material. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Mullins, Jeremiyah (Jeremiyah) - Burcin, William (Billy) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production | Steinbach, William (Bill) - Pavlosky, Richard (Rick) | Labor work package 1M17ESLLC223 Material work package 1M17ESL1N223 | 1/08/2016 - LM Production is directed/authorized to generate for the Technology Part Task Trainer hardware listed below. LM Production shall notify Bill Steinbach (1511) once the kit is available for delivery. Part Cost Number Nomenclature Qty Each RDD Work Package N146440 128 GB 2.5in 3 $1,750 4/28/2017 1M17ESL1N223 Hdw 1M17ESLLC223 Labor 7430420-00 Evir Sensing Mod 1 $2,040 4/28/2017 1M17ESL1N223 Hdw 1M17ESLLC223 Labor | Email Note: From R. Pavlosky dated 21 March 2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00009 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI08 to TI16 SSN 779 System, Pre-Cable & Unit 6201 Spares |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI08 to TI16 Sonar System Virginia Modernization SSN 779. The Period of Performance (POP) for this effort shall be from March 2017 thru September 2019. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N148500-200 Sonar System 1 0212AA See Attachment Provided Unit 6201 0212AD See Attachment Provided Note: Unit 6201 Assembly is under the top level System BOM but has its own funding Clin and work packages provided with Attachment. N148547-1 Pre-Cable kit 1 0212AB See Attachment Provided Note: The SSN 779 Pre-Cable kit was ordered under FEA (Z-2017-FEA-5), PCD 17-ARCI FY17 TI16 Production-LMDM-PCD0004. Operations (J. Mullins) shall ensure that all charges for the Pre-Cable kit under the FEA are moved to the funded Pre-Cable kit Clin 0212AB. N165080-1 Spares kit 1 0212AC Not Funded at this time. 6201 Spares 0212AE See Attachment Provided Note: Unit 6201 Spares under the Top Level Spares BOM (N165080-1) has its own funding Clin and work packages provided with Attachment. | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00010 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI12 to TI16 SSN 783 System, & Pre-Cable. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI12 to TI16 Sonar System Virginia Modernization SSN 783. The Period of Performance (POP) for this effort shall be from March 2017 thru September 2019. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N148500-500 Sonar System 1 0212BK See Attachment Provided Unit 6201 0212BN See Attachment Provided Note: Unit 6201 Assembly is under the top level System BOM but has its own funding Clin and work packages provided with Attachment. N148547-1 Pre-Cable kit 1 0212BL See Attachment Provided | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00011 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI10 to TI16 SSN 785 System & Pre-Cable. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI10 to TI16 Sonar System Virginia Modernization SSN 785. The Period of Performance (POP) for this effort shall be from March 2017 thru September 2019. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N148500-400 Sonar System 1 0212BA See Attachment Provided N148547-1 Pre-Cable kit 1 0212BB See Attachment Provided | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00012 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI10 to TI16 SSN 775 System, Pre-Cable. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI10 to TI16 Sonar System Virginia Modernization SSN 775. The Period of Performance (POP) for this effort shall be from March 2017 thru September 2019. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N148500-300 Sonar System 1 0212AJ See Attachment Provided Unit 6201 0212AM See Attachment Provided Note: Unit 6201 Assembly is under the top level System BOM but has its own funding Clin and work packages provided with Attachment. N148547-1 Pre-Cable kit 1 0212AK See Attachment Provided | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00013 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI10 to TI16 SSN 774 System, Pre-Cable. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI02 to TI16 Sonar System Virginia Modernization SSN 774. The Period of Performance (POP) for this effort shall be from March 2017 thru September 2019. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N148500-100 Sonar System 1 0212AU See Attachment Provided Unit 6201 0212AY See Attachment Provided Note: Unit 6201 Assembly is under the top level System BOM but has its own funding Clin and work packages provided with Attachment. N148547-1 Pre-Cable kit 1 0212AV See Attachment Provided | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00014 | 3/22/2017 | Approved |  |  | William Jones | 3/22/2017 |  |  | 17-ARCI FY17 TI16 Production-LMDM-PCD00014A | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI12 to TI16 SSN 21 System. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI12 to TI16 SSN 21 Sonar System. The Period of Performance (POP) for this effort shall be from March 2017 thru June 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N160100-10 Sonar System 1 0214AA See Attachment Provided | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. Email Note: From S. Zajkowski dated 22 March 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00014A | 4/10/2017 | Approved |  |  | William Jones | 4/10/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive to generate for FY16 TI12 to TI16 SSN 21 System & Pre-Cable kit. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Murphy, Megan (Megan) - Mullins, Jeremiyah (Jeremiyah) - Kashdin, Kyra (Kyra) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | All work package target budgets are provided as an attachment with this PCD. | 4/10/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI12 to TI16 SSN 21 Pre-Cable kit (N150130-1). The Period of Performance (POP) for this April 2017 thru June 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. ___________________________________________________________________________ 03/22/2017 The purpose of this PCD is to serve as an Initial WAD P00014, authorizing the procurement, manufacturing and labor efforts for FY17 TI12 to TI16 SSN 21 Sonar System. The Period of Performance (POP) for this effort shall be from March 2017 thru June 2018. Note: Per PPMD Section 5.5.3 all CAM's are required to open and close their respective work packages. This is accomplished by the CAM filling out Open/Close Charge ID Macro contained in folder 40 on the EVM portal. Note: For all Required Delivery Dates (RDD) Please reference the Installation Planning Matrix. Part Contract Number Nomenclature Qty Clin Work Package N160100-10 Sonar System 1 0214AA See Attachment Provided N150130-1 Pre-Cable kit 1 0214AB See Attachment Provided | Contract N00024-15-C-6222 Mod P00014 dated 3 March 2017. Email Note: From S. Zajkowski dated 22 March 2017. Email Note: From S. Zajkowski dated 7 April 2017. |  |  | ARCI ES 6222 iWAD 1MFY17 P00014 (006).xlsx
17-ARCI FY17 TI16 Production-LMDM-PCD00015 | 3/28/2017 | Approved |  |  | William Jones | 3/28/2017 |  |  | Current | M7F4 | Jones, William | Program Control Directive authorizing End of Life buy for TI16 FY18 Production requirements. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Mullins, Jeremiyah (Jeremiyah) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production | DeRancy, Daniel (Daniel) | FEA work package 1M0FEA17IC18 shall be used for this effort. | 03/27/2017 Jeremiyah Mullins (LM Manassas) is authorized/directed to generate for End of Life (EOL) Integrated circuit hardware listed below to support ARCI/Virginia TI16 in FY18 Production requirements. The Integrated Circuits are used on the Power Control Module for the PDD's and the Functionality Module. These IC's will go End of Life (EOL) 1 June 2017. These assets shall only be used for ARCI TI16 (SSBN/Seawolf/Virginia) Sonar Systems only. Mfg Part Part Total Work Number Number Nomenclature Qty Cost Package N106431 EPM9560ARC208-10N Int Circuit 144 $38,340 1M0FEA17IC18 79C1002-00 EPM7256SRC208-15N Int Circuit 21 $ 1,995 1M0FEA17IC18 | Z-2017-FEA-18 Initial ARCI Production Procurement of Integrated Circuits. Email Note: From Michelle Bennett dated 23 March 2017.
17-ARCI FY17 TI16 Production-LMDM-PCD00016 | 4/18/2017 | Approved |  |  | William Jones | 4/18/2017 |  |  | Current | M7F4 | Jones, William | Prodgram Control Directive to order Technology Part Task Trainer (TPTT), Lap Top material. |  | N00024-15-C-6222 (FY17 TI16 Production) | Myers, Janet (Janet) - Mullins, Jeremiyah (Jeremiyah) - Burcin, William (Billy) | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production | Steinbach, William (Bill) - Pavlosky, Richard (Rick) | Labor work package 1M17ESLLC223 Material work package 1M17ESL1N223 | 4/18/2017 - LM Production is directed/authorized to generate for the Technology Part Task Trainer hardware listed below. LM Production shall notify Bill Steinbach (1511) once the kits are available for delivery. Note: All material in the Sonar Lap top kits are required except for the Lap Tops P/N N146823-1 Item 25 on the N139894-1 BOM. We already have the Laptops (N146823-1) for the kits but need two sets of the remaining items. Part Cost Number Nomenclature Qty Each RDD Work Package N139894-1 Sonar Lap top 2 $800 5/5/2017 1M17ESL1N223 Hdw 1M17ESLLC223 Labor | Email Note: From B Steinbach dated 4/13/2017.
17-ARCI Production-LMDM-PCD00001 | 1/26/2017 | Approved |  |  | Joseph Fanto | 1/26/2017 |  |  | Current | M7F5 | Eubank, Joey | PPM Delegation of Authority | 1/30/2017 | N00024-15-C-6222 (FY17 TI16 Production) , N00024-15-C-6222 (FY16 TI16 Prod) , N00024-11-C-6294 (FY16 TI14 Production) , N00024-15-C-6222 , N00024-11-C-6294 (FY15 Prod) , N00024-11-C-6294 (FY14 Prod) |  | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Vest, Rita , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kong, Melinda , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Colleyacme, Mark , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Buenrostro, Alvaro , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Baumann, Kristine , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen , Abruzzo, Ludwig | FY14 ARCI/Va Production , ARCI Production , ARCI FY17 TI16 Production , ARCI FY16 Production , ARCI FY15 Production | ARCI Production |  | N/A | ARCI Production (N00024-11-C-6294 & N00024-15-C-6222) SAP Project IDs: 1MT14A, 1MFY15, 1MFY16, 1MFY6A, 1MT16A, 1MSSBN, 1MFY17 PPM Delegation of Authority ARCI Production Program Management Director, Joe Fanto, hereby delegates his authority to sign the following EVM documents (CPRs, EACs, CEAC's BCRs, ECRs, WADs, VARs, Open / Close Charge Numbers) to Joe Eubank – ARCI Production Program Sr Manager ARCI Production Program Sr Manager Joe Eubank, in the instance that he is unavailable, hereby delegates his authority to sign the following EVM documents (BCRs, ECRs, WADs, VARs, Open / Close Charge Numbers) to Bill Jones – ARCI Production Program Manager The following Control Account Managers (CAMs), in the instance that they are unavailable, hereby delegate authority to sign the following EVM documents(BCRs, ECRs, VARs, CEACs, Open / Close Charge Numbers: CAM Back-up Bill Jones Joe Eubank Randy Charlsen Jon Lane Megan Murphy Kyra Kashdin Kyra Kashdin Megan Murphy Keith Scully Megan Murphy Jeremiyah Mullins Janet Myers Adam Neckar Jaclyn Bloss-Bell Chris Johns David Lonnquest The following Finance staff are delegated authority to sign the following EVM documents (BCR's, CEAC's,ECR's, VAR's, Open/Close Charge Numbers) Sue Waugh Karen Williams Jeff Lukasik Dan Derancy Greg Chesterson The following Master Planning staff are delegated authority to sign the following EVM documents (BCR's): Dom Palumbo Wayne Gorsuch Savannah Trump
Draft-001311 | 4/27/2017 | Submitted | [6 empty] | Current | M7F5 | Eubank, Joey | Sample PCD for Approval |  | N00024-15-C-6222 (FY17 TI16 Production) |  | Zajkowski, Stephen , Yerkes, Paul , Williams, Karen , Waugh, Susan , Vidrascu, Radu , Underwood, Peggy , Trump, Savannah , Thornton, Patrick , Thomas, Kenneth , Spittle, Jesse , Scully, Keith , Randall, David , Prutzman, Jason , Parrott, Renee , Palumbo, Dominic , Oliver, Stacey , Neckar, Adam , Myers, Janet , Murphy, Megan , Mullins, Jeremiyah , Menendez, Emanuel , Mason, Deborah , Macdonald, Gina , Lukasik, Jeffrey , Lemus, Nimssi , Lane, John , Kashdin, Kyra , Jones, William , Idris, Hind , Hill, Wayne , Griffith, Stanley , Grayson, Bobbi , Gorsuch, Wayne , Ferreri, Karen , Fanto, Joseph , Eubank, Joey , Eisenbaum, Jason , Domergue, Juan , Chesterson, Gregory , Charlsen, Randolph , Cashin, Jack , Calesaric, Steve , Burcin, William , Bloss-Bell, Jaclyn , Benson, Robert , Baxter, Steven , Batz, David , Batt, Lisa , Barbour, Ikeeia , Baldwin, Kathleen | ARCI FY17 TI16 Production | ARCI FY17 TI16 Production |  | Labor work package 1MXXXXXXXXXX Material work package 1MXXXXXXXXXX | 4/27/2017 - XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX XXXXXXXXXXXX Part Cost Number Nomenclature Qty Each RDD NXXXXXX-X XXXXXXXXXXXX X $XXX MM/DD/YYYY