## Notes
1 | Actionable data has a higher priority in the message que than non-actionable data.

## Deployments
TASK_ID | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 | Deployments
2 | October '09
| MIMOSA Baseline |  |  |  | 2009-09-21
3 | Development Code Freeze |  |  | 2009-09-30 | 2009-09-30
4 | Functional Test |  |  | 2009-10-01 | 2009-10-06
5 | Production Deployment |  |  | 2009-10-07 | 2009-10-07
6 | Production Test |  |  | 2009-10-08 | 2009-10-08
7
8
9
10 | November '09
| MIMOSA Views |  |  |  | 2009-10-15
11 | Development Code Freeze |  |  | 2009-11-02 | 2009-11-02
12 | Functional Test |  |  | 2009-11-03 | 2009-11-06
13 | Production Deployment |  |  | 2009-11-10 | 2009-11-10
14 | Production Test |  |  | 2009-11-12 | 2009-11-12
15
16
17
18 | December '09
19 | Development Code Freeze |  |  | 2009-12-01 | 2009-12-01
20 | Functional Test |  |  | 2009-12-02 | 2009-12-07
21 | Production Deployment |  |  | 2009-12-08 | 2009-12-08
22 | Production Test |  |  | 2009-12-09 | 2009-12-09
23
24
25
26 | January '10
27 | Development Code Freeze
28 | Functional Test
29 | Production Deployment
30 | Production Test
31
32
33
34 | February '10
35 | Development Code Freeze
36 | Functional Test
37 | Production Deployment
38 | Production Test
39
40
41
42 | March '10
43 | Development Code Freeze
44 | Functional Test
45 | Production Deployment
46 | Production Test
47
48
49

## CCDMER
TASK_ID | Status | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | LOGSA Common CBM Enterprise Repository (CCBMER) Implementation Plan
2 |  | AV-1 - Product Description
3 | Done | Preliminary draft |  |  |  | 2009-08-24
4 |  | Draft |  |  |  | 2009-08-31
Release 1
5 |  | Staffing
6 |  | Team lead |  |  |  | 2009-09-01
7 |  | Documentator
8 |  | DoDAF experience
9 |  | Enterprise/System Architect experience
10 |  | MS Viso
11 |  | Web services
12 |  | DoDAF Training
13 |  | 3-day $1,660-2,200 5-DAY $2,700
14 |  | Tools and File Formats Used
15 | Done | MS Office 2007 |  |  |  | 2009-08-19
16 | Requested | MS Project 2003 or later (Qty: 2) |  |  |  | 2009-08-27
17 | Done | MS Visio Professional 2003 or later (Qty: 2) |  |  |  | 2009-08-19
18 |  | IBM Rational - System Architect
19 | Hold | $1,431 - IBM Rational Software Architect Standard Edition Authorized User Initial Fixed Term License + SW Subscription & Support 12 Months (D0524LL)
20 | Hold | $ - IBM® Rational® System Architect® for DoDAF Add On
21 | Hold | $ - DoDAF_ABM Add On
22 |  | Sparx Systems - Enterprise Architect
23 | Hold | $239 - Corporate Edition Standard License (SKU: EACORP)
24 | Hold | $145 - DoDAF-MODAF Technology Standard Edition (SKU: MDGDoDAF-MODAF)
25 |  | Findings
26 |  | - Analysis Results
27 |  | - Recommendations
28
29
30 |  | OV-1 - High-Level Operational Concept Graphic
31
32 |  | CCCBMDW boundaries
33 |  | Current LIW boundaries (transactional)
34 |  | ILAP (maintenance)
35
36 |  | (operational)
37
38 |  | Current Operations Graphic
39
40
41 |  | 2011 Operational Concept
42
43
44 |  | 2016 Operational Concept
45
46
47 |  | OV-4 - Organizational Chart
48
49
50 |  | OV-5 - Operational Activity Model
51 |  | • Operational activites (or tasks)
52 |  | • Input and Output (I/O) flows between activites
53 |  | • Input and Output (I/O) flows to/from activities outside the scope of the architiecture
54
55
56
57 |  | Army Bulk CBM DATA (ABCD) file specification | Where does this stand?
58
59
60
61 |  | MIMOSA
62 |  | RDR Request |  |  |  |  | 3
63
64 |  | Tech-CDE
65 |  | Harden the CDE server
66 |  | Permanent ID IIS security | [5 empty] | Jamehl Law, David Ritter
67 |  | URL for CDE
68 |  | Restore all the broken data links
69 |  | Westar
70 |  | DRS
71
72
73 |  | Tech-CDE production installation plan
74 |  | Permanent ID IIS security
75 |  | URL for CDE
76
77
78 |  | Documentation
79 |  | Best practices | [5 empty] | Tony
80 |  | Implemenation guide | [5 empty] | Tony
81
82 |  | Papers
83 |  | Lessons learned | [5 empty] | Tony
84
85
86 |  | Bulk/binary File Repository (UNIX/Windows)
87 |  | Army binary file formats
88 |  | 2011
89 |  | 2012
90 |  | Pipeline & storage for bulk
91 |  | Database entries bulk/binary files (UNIX)
92 |  | Bulk/binary file processing
93 |  | Received
94 |  | - Establish unique identifier for bulk/binary file
95 |  | - Indentify item
96 |  | - Indentify item serial number
97 |  | - Record in OLTP & (MIMOSA)
98
99 |  | Logged
100 |  | Validation parse
101 |  | Parse for
102 |  | - Usage
103 |  | - Availability
104 |  | - CBM
105 |  | Integrate other Army data | 1
106
107 |  | Actionable - How is CBM identified that needs true warehousing?
108 |  | Non-Actionable
109
110
111 |  | Map PFSA to MIMOSA
112
113
114 |  | Maintenance and Event History
115 |  | Schedule meeting to discuss events
116 |  | Review proposed events
117 |  | Discuss zero-duration events
118 |  | Discuss mapping to MIMOSA
119 |  | Transaction facts in CBMWH
120 |  | Roll-up facts in CBMWH
121
122
123 |  | Maintenance Roll-ups
124 |  | CWT => cwt_cnt, min, max, sum, avg, mean _50, _85
125 |  | Schedule meeting with Rick | [5 empty] | Gene
126
127
128
129
130 |  | Ontology (defines a common vocabulary to share information in a domain.) | [5 empty] | Tony
131 |  | Management
132 |  | MIMOSA is the repository for the ontology
133 |  | Review mapping |  |  | 2008-08-11 |  |  | Tony, Ken, Gene
134
135
136 |  | Taxonomy (practice and science of classification) | [5 empty] | Tony
137 |  | Management | [5 empty] | Rick, Dave, Chris, Tony, Ken, Gene
138 |  | Processes
139 |  | Review and approval
140 |  | Physical maintenance
141 |  | Where is the master housed
142 |  | Distribution
143
144
145
146 |  | LOGSA Enterprise Asset Management Registry
147
148
149
150 |  | LOGSA Common CBM Data Warehouse (CCBMDW) Implemenation Plan
151
152
153
154
155 |  | LOGSA Bulk File Management
156 |  | Army Standard Binary Adapter
157 |  | Develop requirememts |  |  | 2008-09-01
158 |  | Prototype with DRS data |  |  | 2008-09-01 | 2008-10-31
159 |  | Review prototype |  |  | 2008-10-31
160 |  | Review MetaData |  |  | 2008-10-31
161 |  | Rarser development |  |  |  | 2009-01-31
162 |  | Recommend to G-6 |  |  |  | 2009-02-28
163
164
165
166 |  | Logistic Management Information (LMI - LSAR) Warehouse (PowerLog-J - Unity)
167
168
169
170 |  | LOGSA Enterprise Service Bus
171
172
173
174 |  | LOGSA CDE Management
175
176
177
178 |  | SAS Data Miner
179
180
181
182 |  | Text Miner
183
184
185
186 |  | LIA
187 |  | CBM+ POA | [5 empty] | Tony
188 |  | Database at LOGSA
189 |  | IDC Global Data Manager installed (data transfer)
190 |  | CDC - Java class to insert ??cwr svsr??
191
192
193
194
195 |  | Tank-Automotive and Armament Command (TACOM)
196 |  | DRS
197 |  | MOA | [5 empty] | Chris
198 |  | SIA | [5 empty] | Chris, Matthew
199 |  | Portals
200 |  | Migrate CDRS data to Oracle DB at LOGSA | [5 empty] | Tony
201 |  | Setup Oracle application services | [5 empty] | Tony
202 |  | DRS web services onto DOD GIG (SOA) | [5 empty] | Tony
203
204
205
206 |  | Aviation and Missile Command (AMCOM)
207 |  | Westar
208 |  | Track CBMDW database changes | [5 empty] | Gene, Tony
209 |  | Track platorms and assets per platform | [5 empty] | Gene, Tony
210
211
212
213 |  | Army Oil Analysis Program (AOAP)
214 |  | Where is the data?
215 |  | Map data elements to MIMOSA.
216
217
218

## ABCD Tech Spec
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | Army Bulk CBM DATA (ABCD) file specification
2 | Started | LIA revisions |  |  | 2009-09-01 | 2009-09-08 |  | Tony
3 |  | Task
4
5
6
7
8
9
10

## MIMOSA
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | MIMOSA
2 |  | AV-1 - Product Description
3 |  | • Architecture Project Identification
4 |  | - Name
5 |  | - Architect
6 |  | - Organization Developing the Architecture
7 |  | - Assumptions and Constraints
8 |  | - Approval Authority
9 |  | - Date Completed
10 |  | - Level of Effort and Projected and Actual Costs to Develop the Architecture
11 |  | • Scope: Architecture View(s) and Products Identification
12 |  | - Views and Products Developed
13 |  | - Time Frames Addressed
14 |  | - Organizations Involved
15 |  | • Purpose and Viewpoint
16 |  | - Purpose, Analysis, Questions to be Answered by Analysis of the Architecture
17 |  | - From Whose Viewpoint the Architecture is Developed
18 |  | • Expected Results
19 |  | • Types of Analyses
20 |  | • Context
21 |  | - Mission
22 |  | - Doctrine, Goals, and Vision
23 |  | - Rules, Criteria, and Conventions Followed
24 |  | - Tasking for Architecture Project and Linkages to Other Architectures
25 |  | • Tools and File Formats Used
26 |  | • Findings
27 |  | - Analysis Results
28 |  | - Recommendations
29
30
31 |  | OV-1 - High-Level Operational Concept Graphic
32
33
34 |  | OV-4 - Organizational Chart
35
36
37 |  | OV-5 - Operational Activity Model
38 |  | • Operational activites (or tasks)
39 |  | • Input and Output (I/O) flows between activites
40 |  | • Input and Output (I/O) flows to/from activities outside the scope of the architiecture
41
42
43 |  | MIMOSA Baseline (MIMOSA_BL) |  | 17D
44 |  | RDR
45 |  | Take over RDR_001
46 | Done | Get password |  |  | 2009-08-28 | 2009-08-28
47 | Done | Clear the schema | DH - Yes |  | 2009-08-28 | 2009-09-14
48 |  | LEC Core Schema Setup
49 |  | E-mail account "logsa.mimosa@conus.army.mil"
50 | Done | Dave Hendricks input | Yes |  |  | 2009-09-14
51 |  | Chris Booth input (3 od e-mail addresses)
52 |  | E-mail the helpdesk about the setup process |  |  | 2009-09-14
53 |  | Request e-mail addresses
54 |  | Incorporate into maintain_xxxxxx_world procedure
55 |  | Control Processes
56 |  | 170 -Sequences
57 | 75% | mimosa_bl_process_control_seq |  |  | 2009-09-10
58 | 75% | mimosa_bl_process_log_seq |  |  | 2009-09-10
59 | 75% | mimosa_bl_process_ref_seq |  |  | 2009-09-10
60 |  | 180 - Tables
61 |  | mimosa_bl_emal_addr_grp_ref
62 |  | mimosa_bl_emal_addr_grp_ref_audt
63 |  | mimosa_bl_emal_addr_grp_xref
64 |  | mimosa_bl_emal_addr_grp_xref_audt
65 |  | mimosa_bl_emal_addr_ref
66 |  | mimosa_bl_emal_addr_ref_audt
67 | 75% | mimosa_bl_functional_warnings |  |  | 2009-09-01
68 | 75% | mimosa_bl_process_control |  |  | 2009-09-09
69 | 75% | mimosa_bl_process_control_audt |  |  | 2009-09-10
70 | 75% | mimosa_bl_process_log |  |  | 2009-09-09
71 | 75% | mimosa_bl_process_ref |  |  | 2009-09-09
72 | 75% | mimosa_bl_process_ref_audt |  |  | 2009-09-10
73 | 75% | mimosa_bl_processes |  |  | 2009-09-09
74 | 75% | mimosa_bl_processes_hist |  |  | 2009-09-09
75 | 75% | mimosa_bl_tab_size_trk |  |  | 2009-09-09
76 | 75% | std_mimosa_bl_debug_tbl |  |  | 2009-09-01
77 |  | 260 - Functions
78 |  | DATE_ID_TO_DATE
79 |  | DATE_TO_DATE_ID
80 |  | DATE_DIM_ID
81 |  | PRCSS_CNTRL_VAL
82 |  | PRCSS_RUN_FLAG
83 | 75% | mimosa_bl_get_prcss_run_id |  |  | 2009-09-09
84 |  | mimosa_bl_get_prcss_cntrl_val
85 |  | TIME_ID_TO_TIME
86 |  | TIME_TO_TIME_ID
87 |  | FROM_BASE32
88 |  | FAKE_BASE32_UIC
89 |  | PROC_CTRL_CHAR_VAL
90 |  | RUN_REINDEX
91 | 75% | run_today |  |  | 2009-09-09
92 |  | TO_BASE32
93 |  | 270 - Procedures
94 | 75% | maintain_mimosa_bl_world |  |  | 2009-09-01
95 | 75% | mimosa_bl_insupd_processlog |  |  | 2009-09-09
96 | 75% | get_mimosa_bl_process_info |  |  | 2009-09-09
97 | 75% | updt_mimosa_bl_processes |  |  | 2009-09-09
98 | 75% | mimosa_bl_log_cleanup |  |  | 2009-09-09
99 | 75% | mimosa_bl_debugtbl_cleanup |  |  | 2009-09-09
100 | 75% | mimosa_bl_cleanup_weekly |  |  | 2009-09-09
101 | 75% | table_size_tracking |  |  | 2009-09-09
102 |  | 280 - Triggers
103 | 75% | tr_i_mimosa_bl_proces_ctrl_seq |  |  | 2009-09-10
104 | 75% | tr_mimosa_bl_proces_ctrl_audt |  |  | 2009-09-10
105 | 75% | tr_u_mimosa_bl_proc_ctrl_updt |  |  | 2009-09-10
106 | 75% | tr_i_mimosa_bl_process_log_seq |  |  | 2009-09-10
107 | 75% | tr_i_mimosa_bl_process_ref_seq.sql |  |  | 2009-09-10
108 | 75% | tr_mimosa_bl_process_ref_audt.sql |  |  | 2009-09-10
109 | 75% | tr_u_mimosa_bl_proces_ref_updt |  |  | 2009-09-10
110 |  | 310 - Schema_Post_Deployment
111 | 75% | merge_into_mimosa_bl_process_control |  |  | 2009-09-11
112 | 75% | merge_into_mimosa_bl_process_ref |  |  | 2009-09-11
113
114 |  | Build |  |  | 2009-08-31 | 2009-09-10
115 | 90% | MIMOSA_32_Step10_ORACLE_SQLPlus_Create_Tables_and_PKs.sql |  | 1D | 2009-08-28 | 2009-09-01
116 | 90% | MIMOSA_32_Step13_ORACLE_SQLPlus_Enterprise.sql |  | 1D | 2009-09-08 | 2009-09-08
117 | 90% | MIMOSA_32_Step20_ORACLE_SQLPlus_Insert_Ref_Data.sql |  | 1D | 2009-09-09 | 2009-09-09
118 | 90% | MIMOSA_32_Step30_ORACLE_SQLPlus_Create_FKs.sql |  | 1D | 2009-09-10 | 2009-09-10
119 | Done | MIMOSA_32_Step00_ORACLE_SQLPlus_Drop_Tables.sql |  | 1D | 2009-08-31 | 2009-08-31
120 |  | Audit tables for Types
121 | 75% | mimosa_bl_table_ref
122 | 75% | mimosa_bl_table_ref_audt
123 |  | Grants
124 | ? | Tables
125 | ? | Procedures
126 |  | VM folders
127 |  | Pre-Production Support
128 |  | Logs
129 |  | Job
130 |  | DEV - MIMOSA_BL
131 |  | Table Load Deployment |  | 5D | 2009-09-23 | 2009-09-29
132 |  | Validation |  | 1D | 2009-09-30 | 2009-09-30
133 |  | TST - MIMOSA_BL
134 |  | Table Load Deployment |  | 3D | 2009-10-01 | 2009-10-05
135 |  | Validation |  | 1D | 2009-10-06 | 2009-10-06
136 |  | PRD - MIMOSA_BL
137 |  | Table Load Deployment |  | 1D | 2009-10-07 | 2009-10-07
138 |  | Validation |  | 1D | 2009-10-08 | 2009-10-08
139
140
141 |  | MIMOSA Nightly (MIMOSA_BL)
142 |  | Unix logs
143 |  | Schema change tracking
144
145
146
147 |  | MIMOSA Views (MIMOSA)
148 |  | RDR
149 |  | View Build Control |  | 1D | 2009-09-22 | 2009-09-22
150 |  | mimosa_bl_view_ref
151
152 |  | View Build Script |  | 5D | 2009-09-23 | 2009-09-28
153 |  | View Test |  | 5D | 2009-09-29 | 2009-10-06
154 |  | DEV - MIMOSA
155 |  | View Deployment |  | 5D | 2009-10-07 | 2009-10-14
156 |  | Validation |  | 1D | 2009-10-15 | 2009-10-15
157 |  | TST - MIMOSA
158 |  | View Deployment |  | 3D
159 |  | Validation |  | 1D
160 |  | PRD - MIMOSA
161 |  | View Deployment |  | 1D
162 |  | Validation |  | 1D
163
164
165 |  | SED CRIS Replication 1.0
166 |  | RDR
167 |  | Replication Build Control |  | 1D
168 |  | Control Table
169 |  | Control Audit Table
170 |  | Replication Build Script |  | 1D
171 |  | Replication Test |  | 5D
172 |  | DEV
173 |  | Table Replication Deployment |  | 5D
174 |  | Validation |  | 1D
175 |  | TST
176 |  | Table Replication Deployment |  | 3D
177 |  | Validation |  | 1D
178 |  | PRD
179 |  | Table Replication Deployment |  | 1D
180 |  | Validation |  | 1D
181
182
183 |  | SED CRIS Configuration 1.0
184 |  | RDR
185 |  | Configuration Control |  | 1D
186 |  | Configuration Build Script |  | 1D
187 |  | Configuration Test |  | 5D
188 |  | DEV
189 |  | Configuratio Deployment |  | 5D
190 |  | Validation |  | 1D
191 |  | TST
192 |  | Configuratio Deployment |  | 3D
193 |  | Validation |  | 1D
194 |  | PRD
195 |  | Configuratio Deployment |  | 1D
196 |  | Validation |  | 1D
197
198
199 |  | SED CRIS Synchronization 1.0
200 |  | RDR
201 |  | Synchronization Build Control |  | 1D
202 |  | Synchronization Script |  | 1D
203 |  | Synchronization Test |  | 5D
204 |  | DEV
205 |  | Synchronization Deployment |  | 5D
206 |  | Validation |  | 1D
207 |  | TST
208 |  | Synchronization Deployment |  | 3D
209 |  | Validation |  | 1D
210 |  | PRD
211 |  | Synchronization Deployment |  | 1D
212 |  | Validation |  | 1D
213
214
215 |  | CLOE LDB CRIS Replication 1.0
216 |  | RDR
217 |  | Table Replication Control |  | 1D
218 |  | Table Replication Data |  | 1D
219 |  | Table Replication Script |  | 5D
220 |  | Table Replication
221 |  | agent
222 |  | agent_type
223 |  | alarm_type
224 |  | as_readiness_type
225 |  | asset
226 |  | asset_on_segment
227 |  | asset_type
228 |  | asset_type_child
229 |  | binary_num_data
230 |  | blob_content_type
231 |  | blob_data_type
232 |  | change_patt_type
233 |  | cris_instance
234 |  | criticality_scale_type
235 |  | data_qual_type
236 |  | data_source
237 |  | data_source_type
238 |  | eng_study_code
239 |  | eng_study_entry
240 |  | eng_study_type
241 |  | eng_unit_enum
242 |  | eng_unit_type
243 |  | enterprise
244 |  | enterprise_type
245 |  | ev_num_data_type
246 |  | event_type_child
247 |  | manufacturer
248 |  | meas_event
249 |  | meas_loc_type
250 |  | meas_location
251 |  | mevent_blob_data
252 |  | mevent_blob_type
253 |  | mevent_num_alarm
254 |  | mevent_num_data
255 |  | mloc_calc_type
256 |  | mloc_type_child
257 |  | model
258 |  | model_blob_data
259 |  | model_child
260 |  | network
261 |  | network_conn_type
262 |  | network_type
263 |  | num_al_assoc_reg
264 |  | num_alarm_reg
265 |  | priority_level_type
266 |  | ref_unit_type
267 |  | request
268 |  | request_for_sg_prop_event
269 |  | row_status_type
270 |  | segment
271 |  | segment_child
272 |  | segment_chr_data
273 |  | segment_event
274 |  | segment_num_data
275 |  | segment_type
276 |  | segment_type_child
277 |  | severity_level_type
278 |  | sg_as_event_type
279 |  | sg_chr_dat_type
280 |  | sg_comp_work_for_sg_prop_event
281 |  | sg_completed_work
282 |  | sg_ev_meas_event
283 |  | sg_event_num_data
284 |  | sg_network_connect
285 |  | sg_num_dat_type
286 |  | sg_prop_ev_link
287 |  | sg_prop_ev_sg_ev
288 |  | sg_proposed_event
289 |  | sg_recommendation
290 |  | sg_remaining_life
291 |  | sg_req_for_work
292 |  | sg_sol_pack
293 |  | site
294 |  | site_database
295 |  | site_type
296 |  | solution_pack_type
297 |  | solution_package
298 |  | solution_package_step
299 |  | standard_data_type
300 |  | tr_axis_dir_type
301 |  | trans_type
302 |  | transducer
303 |  | valid_as_type_on_sg_type
304 |  | work_audit_type
305 |  | work_item_type
306 |  | work_manage_type
307 |  | work_num_data_type
308 |  | work_order
309 |  | work_order_for_sg_prop_ev
310 |  | work_req_num_data
311 |  | work_request
312 |  | work_request_audit
313 |  | work_step
314 |  | work_task_type
315 |  | Table Replication Load
316 |  | DEV
317
318 |  | TST
319
320 |  | PRD
321
322
323 |  | CLOE LDB CRIS Synchronization 1.0
324 |  | RDR
325 |  | Table Replication Control |  | 1D
326 |  | Table Replication Data |  | 1D
327 |  | Table Replication Script |  | 5D
328 |  | Table Replication
329 |  | agent
330 |  | agent_type
331 |  | alarm_type
332 |  | as_readiness_type
333 |  | asset
334 |  | asset_on_segment
335 |  | asset_type
336 |  | asset_type_child
337 |  | binary_num_data
338 |  | blob_content_type
339 |  | blob_data_type
340 |  | change_patt_type
341 |  | cris_instance
342 |  | criticality_scale_type
343 |  | data_qual_type
344 |  | data_source
345 |  | data_source_type
346 |  | eng_study_code
347 |  | eng_study_entry
348 |  | eng_study_type
349 |  | eng_unit_enum
350 |  | eng_unit_type
351 |  | enterprise
352 |  | enterprise_type
353 |  | ev_num_data_type
354 |  | event_type_child
355 |  | manufacturer
356 |  | meas_event
357 |  | meas_loc_type
358 |  | meas_location
359 |  | mevent_blob_data
360 |  | mevent_blob_type
361 |  | mevent_num_alarm
362 |  | mevent_num_data
363 |  | mloc_calc_type
364 |  | mloc_type_child
365 |  | model
366 |  | model_blob_data
367 |  | model_child
368 |  | network
369 |  | network_conn_type
370 |  | network_type
371 |  | num_al_assoc_reg
372 |  | num_alarm_reg
373 |  | priority_level_type
374 |  | ref_unit_type
375 |  | request
376 |  | request_for_sg_prop_event
377 |  | row_status_type
378 |  | segment
379 |  | segment_child
380 |  | segment_chr_data
381 |  | segment_event
382 |  | segment_num_data
383 |  | segment_type
384 |  | segment_type_child
385 |  | severity_level_type
386 |  | sg_as_event_type
387 |  | sg_chr_dat_type
388 |  | sg_comp_work_for_sg_prop_event
389 |  | sg_completed_work
390 |  | sg_ev_meas_event
391 |  | sg_event_num_data
392 |  | sg_network_connect
393 |  | sg_num_dat_type
394 |  | sg_prop_ev_link
395 |  | sg_prop_ev_sg_ev
396 |  | sg_proposed_event
397 |  | sg_recommendation
398 |  | sg_remaining_life
399 |  | sg_req_for_work
400 |  | sg_sol_pack
401 |  | site
402 |  | site_database
403 |  | site_type
404 |  | solution_pack_type
405 |  | solution_package
406 |  | solution_package_step
407 |  | standard_data_type
408 |  | tr_axis_dir_type
409 |  | trans_type
410 |  | transducer
411 |  | valid_as_type_on_sg_type
412 |  | work_audit_type
413 |  | work_item_type
414 |  | work_manage_type
415 |  | work_num_data_type
416 |  | work_order
417 |  | work_order_for_sg_prop_ev
418 |  | work_req_num_data
419 |  | work_request
420 |  | work_request_audit
421 |  | work_step
422 |  | work_task_type
423 |  | Table Replication Load
424 |  | DEV
425
426 |  | TST
427
428 |  | PRD
429
430 |  | CLOE LDB CRIS Configuration 1.0
431 |  | RDR
432 |  | Table Load Control |  | 1D
433 |  | Table Load Data |  | 1D
434 |  | Table Load Script |  | 5D
435 | Started | Table Load (CLOE LDB CONFIG TYPES.xlsx)
436 | Started | alarm_type
437 | Started | Delete |  | .5D
438 | Started | Merge |  | .5D
439 | Started | asset_type |  | .125D
440 | Started | asset_type_child |  | .125D
441 | Started | blob_content_type |  | .125D
442 | Started | blob_data_type |  | .125D
443 | Started | data_source_type |  | .125D
444 | Started | eng_unit_type |  | .125D
445 | Started | eng_unit_enum |  | .125D
446 | Started | event_type_child |  | .125D
447 | Started | ev_num_data_type |  | .125D
448 | Started | meas_loc_type |  | .125D
449 | Started | mevent_blob_type |  | .125D
450 | Started | network_type |  | .125D
451 | Started | priority_level_type |  | .125D
452 | Started | segment_type |  | .125D
453 | Started | segment_type_child |  | .125D
454 | Started | severity_level_type |  | .125D
455 | Started | sg_as_event_type |  | .125D
456 | Started | sg_chr_dat_type |  | .125D
457 | Started | sg_num_dat_type |  | .125D
458 | Started | solution_pack_type |  | .125D
459 | Started | work_num_data_type |  | .125D
460 | Started | work_task_type |  | .125D
461 |  | CLOE LDB Configuratiom 1.0 Replication
462 |  | DEV
463 |  | MIMOSA Baseline replication |  | 5D
464 |  | Table Load Deployment |  | 5D
465 |  | Validation |  | 1D
466 |  | TST
467 |  | Table Load Deployment |  | 3D
468 |  | Validation |  | 1D
469 |  | PRD
470 |  | Table Load Deployment |  | 1D
471 |  | Validation |  | 1D
472
473

## Asset Mgmt Registry
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | LOGSA Enterprise Asset Management Registry
2 |  | Jonathan call
3 |  | SIWG Meeting Huntsville |  |  | 2009-09-22 | 2009-09-23
4
5
6
7
8
9
10
11
12 |  | Migrate PFSAWH dimension identifty assignment from LIWWH to LIDB.
13
14
15
16
17
18
19
20
21
22
23

## CCBMDW
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | LOGSA Common CBM Data Warehouse (CCBMDW) Implemenation Plan
2 |  | Section 1
3 |  | Task
4
5 |  | RDR Request |  |  |  |  | 3
6
7
8
9
10
11
12
13 |  | CBMWH
14
15 |  | Army binary data storage strategy
16 |  | Meeting |  |  | 2008-08-11 |  |  | Rick, Dave, Chris, Tony, Ken, Gene
17
18 |  | LOGSA CBM data warehousing strategy slides |  |  |  | 2008-09-01
19
20 |  | Terry Edwards CIO G-6 CBM Meeting |  |  |  | 2008-09-11
21 |  | Stephen Kelleher
22 |  | 1 - MIMOSA is not a data warehouse
23 |  | a - What it is
24 |  | b - How to use it
25 |  | c - How does it is integrated into the LOGSA CBM strategy
26
27 |  | 2 - Time series data
28 |  | Whether it even needs to be stored st that level
29
30 |  | 3 - Volumetrics
31
32
33 |  | Inputs to LOGSA
34 |  | STAMIS
35 |  | ULLS
36
37
38 |  | CBMWH_AUDIT_LOG
39
40
41 |  | CBMWH_ELT_ERROR_LOG
42
43
44 |  | DATE_DIM
45
46
47 |  | TIME_DIM
48
49
50 |  | ITEM_DIM
51
52
53 |  | ITEM_SN_DIM
54 |  | Develop use cases
55 |  | LIW
56 |  | PFSA
57 |  | LIDB
58 |  | LIWWH
59 |  | PUSE
60 |  | Contractors
61 |  | DRS
62 |  | Westar
63 |  | LIA
64 |  | CBM+ POA
65 |  | Capture metadata in MIMOSA
66 |  | Define data elements
67 |  | Define common data elements across LIW groups.
68 |  | Define dimension material view for replication back to transactional data (LIDB).
69 |  | Define what data can be updated automatically and where.
70 |  | Define priority of source data.
71 |  | Define SN process for when a new SN is found or needed.
72 |  | Define manual update processes and where they happen.
73 |  | Sync between OLTP and warehouse (both directions.)
74 |  | Develop MIMOSA compiant message to transmit dimension.
75
76
77 |  | FORCE_UNIT_DIM
78 |  | Develop use cases
79 |  | LIW
80 |  | PFSA
81 |  | LIDB
82 |  | LIWWH
83 |  | PUSE
84 |  | Contractors
85 |  | DRS
86 |  | Westar
87 |  | LIA
88 |  | CBM+ POA
89 |  | Capture metadata in MIMOSA
90 |  | Define data elements
91 |  | Define common data elements across LIW groups.
92 |  | Define dimension material view for replication back to transactional data (LIDB).
93 |  | Define what data can be updated automatically and where.
94 |  | Define priority of source data.
95 |  | Define UIC process for when a new UIC is found or needed.
96 |  | Define manual update processes and where they happen.
97 |  | Sync between OLTP and warehouse (both directions.)
98 |  | Develop MIMOSA compiant message to transmit dimension.
99
100
101 |  | LOCATION_DIM
102
103 |  | Platform Integration Management Module
104
105

## LMI (PowerLog J)
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | Logistic Management Information (LMI - LSAR) Warehouse (PowerLog-J - Unity)
2 |  | Section 1
3 |  | Task
4
5
6
7
8
9
10

## Service Bus
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | LOGSA Enterprise Service Bus
2 |  | Install LOGSA SOA on CDE
3 | Done | Get IP address (158.2.104.231) |  |  | 2009-09-08 | 2009-09-08 |  | Tony
4 | Done | Get access to CDE box |  |  | 2009-09-08 | 2009-09-08 |  | Szymanski, Paul
5 | Started | Track down Rodney and find out what the plan is | [5 empty] | Rutledge, Rodney
6
7
8
9
10
11
12 |  | Taxonomy Management Tool
13 |  | Develop requirememts |  |  | 2008-10-01
14 |  | Prototype interface |  |  |  | 2008-11-30
15 |  | Review prototype interface |  |  | 2008-11-30
16 |  | Additional requirements |  |  | 2008-11-30
17 |  | Initial caabilities done |  |  |  | 2009-01-31
18 |  | Integrate into LIW |  |  |  | 2009-03-31
19
20
21
22 |  | Visual CBM+ Tool
23 |  | Develop requirememts |  |  | 2008-10-01
24 |  | Prototype DRS portal |  |  | 2008-10-01 | 2008-11-30
25 |  | Review prototype portal |  |  | 2008-11-30
26 |  | Add IBM services |  |  |  | 2009-03-31
27 |  | Initial caabilities done |  |  |  | 2009-03-31
28 |  | Integrate into LIW |  |  |  | 2009-06-30
29
30
31

## PFSA
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | Title
2 |  | Section 1
3 |  | Task
4
5
6
7
8
9
10

## Blank
TASK_ID | SCHEMA | TASK | NOTES | DURATION | START DATE | END DATE | PREDECESSOR | RESPONSIBLE
1 |  | Title
2 |  | Section 1
3 |  | Task
4
5
6
7
8
9
10

## Backup
AV-1 - Product Description
• Architecture Project Identification
- Name
- Reference Documents
Condition Based Maintenance Plus DoD Guidebook - May 2008
DoDAF
- Architect
- Organization Developing the Architecture
- Assumptions and Constraints
LIW Security Model
DoDAF
Development standards
- Approval Authority
- Date Completed
- Level of Effort and Projected and Actual Costs to Develop the Architecture
• Scope: Architecture View(s) and Products Identification
- Views and Products Developed
- Time Frames Addressed
- Organizations Involved
• Purpose and Viewpoint
- Purpose, Analysis, Questions to be Answered by Analysis of the Architecture
- From Whose Viewpoint the Architecture is Developed
• Expected Results
• Types of Analyses
• Context
- Mission
- Doctrine, Goals, and Vision
- Rules, Criteria, and Conventions Followed
- Tasking for Architecture Project and Linkages to Other Architectures