## Sheet1
Project Projection for Bulk File Manager
| %Complete | Task | Est. Hours | Dependency | Assigned
I. |  | Concept and Design |  |  |  | I. -
I.A |  | Concept Statement |  |  |  | I.A - Bulk File Management Description and Signoff Approval
I.B |  | Preliminary Design |  |  |  | I.B - Design overview for Management Approval
I.C |  | Design Review |  |  |  | I.C - Design Review with Management
I.C.1 |  | Overview Design |  |  |  | I.C.1 - Overview Design
I.C.2 |  | Requirements Definition Review |  |  |  | I.C.2 - Requirements Defined Review
I.C.3 |  | Functional Design Review |  |  |  | I.C.3 - Functional Design Presentation, Explanation and Review
I.D |  | Design Approval |  |  |  | I.D - Management Approval of Design
II. |  | Environment Setup |  |  |  | II. - Development Setup Environment with scaling to production
II.A |  | Hardware |  |  |  | II.A - Development Hardware Definition in Size and Scope
II.A.1 |  | Servers (bulk file management) |  |  |  | II.A.1 -
II.A.2 |  | Servers(database servers) |  |  |  | II.A.2 -
II.B |  | Software |  |  |  | II.B - Software tools and testing products
II.B.1 |  | Operating System Definition and Specifications |  |  |  | II.B.1 -
II.B.2 |  | Development Tools |  |  |  | II.B.2 -
II.B.3 |  | Testing Tools |  |  |  | II.B.3 -
III. |  | Technical Specifications |  |  |  | III. -
III.A |  | Overview |  |  |  | III.A - Overview of Technical Specifications of Overall System
III.B |  | Component Definition |  |  |  | III.B -
III.B.1 |  | Directory Architecture |  |  |  | III.B.1 - Definition of projected directory design to hold the bulk files. Backup methodology trade-offs, aging of files, roll off process are covered here.
III.B.1.a |  | Bulk Management Process Directory Architecture |  |  |  | III.B.1.a - This is the definition of the directory structure for the Bulk File Management System where each process has its on directory and has the knowledge of the directory where it should put the file when it's processing is complete.
III.B.1.b |  | Long Term Storage Directory and Maintenance |  |  |  | III.B.1.b - Definition of the Long Term Storage and Directory structure. Included here will be a full discussion on the long term maintenance and aging of the files.
III.B.2 |  | Template Definition |  |  |  | III.B.2 - For each process that is built dynamically there is a template
III.B.2.a |  | Forklift |  |  |  | III.B.2.a - This template handles the different sources of incoming files
III.B.2.a.i |  | Library Functions (common) |  |  |  | III.B.2.a.i - Understand the common Library functions needed and identify them for this process
III.B.2.a.ii |  | Library Functions (unique) |  |  |  | III.B.2.a.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.a.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.a.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.2.b |  | Sorter |  |  |  | III.B.2.b - This template handles the re-direction of the files to the process that can actually tag the file within the CCBMWHER
III.B.2.b.i |  | Library Functions (common) |  |  |  | III.B.2.b.i - Understand the common Library functions needed and identify them for this process
III.B.2.b.ii |  | Library Functions (unique) |  |  |  | III.B.2.b.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.b.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.b.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.2.c |  | Cataloger |  |  |  | III.B.2.c - This is the template for the processing that actually 1. rename the file 2. merge key data into the warehouse 3. create sub packages if needed
III.B.2.c.i |  | Library Functions (common) |  |  |  | III.B.2.c.i - Understand the common Library functions needed and identify them for this process
III.B.2.c.ii |  | Library Functions (unique) |  |  |  | III.B.2.c.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.c.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.c.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.2.d |  | Stocker |  |  |  | III.B.2.d - This template is the processing that takes the file(s) and moves them to long term storage.
III.B.2.d.i |  | Library Functions (common) |  |  |  | III.B.2.d.i - Understand the common Library functions needed and identify them for this process
III.B.2.d.ii |  | Library Functions (unique) |  |  |  | III.B.2.d.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.d.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.d.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.2.e |  | Retriever |  |  |  | III.B.2.e - This template is the process that retrieves various combination of files for transmission to the requestor.
III.B.2.e.i |  | Library Functions (common) |  |  |  | III.B.2.e.i - Understand the common Library functions needed and identify them for this process
III.B.2.e.ii |  | Library Functions (unique) |  |  |  | III.B.2.e.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.e.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.e.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.2.f |  | Packager |  |  |  | III.B.2.f - This is the template that packages the files gathered by the retriever for transmitting to the requestor.
III.B.2.f.i |  | Library Functions (common) |  |  |  | III.B.2.f.i - Understand the common Library functions needed and identify them for this process
III.B.2.f.ii |  | Library Functions (unique) |  |  |  | III.B.2.f.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.f.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.f.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.2.g |  | Sender |  |  |  | III.B.2.g - This is the template that sends the 'package' to the requestor.
III.B.2.g.i |  | Library Functions (common) |  |  |  | III.B.2.g.i - Understand the common Library functions needed and identify them for this process
III.B.2.g.ii |  | Library Functions (unique) |  |  |  | III.B.2.g.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.2.g.iii |  | Template defintion with detailed documentation |  |  |  | III.B.2.g.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.3 |  | Composer Defintion |  |  |  | III.B.3 - This section defines the parts and process that builds the processes using the above templates.
III.B.3.a |  | Control Tables |  |  |  | III.B.3.a - The control tables in the Oracle database are the business rules and code snippets that are used to define the code in the respective template.
III.B.3.b |  | Library Modules |  |  |  | III.B.3.b - The library modules are Perl (PM) libraries that provide the functions for the Composer and processes to do tasks. This allows for a single point of maintenance control for all the processes.
III.B.3.c |  | Business Rule Manager(BRM) |  |  |  | III.B.3.c - The business rule manager is the process that allows the functional management of the the business control rules for each of the build and processing processes.
III.B.3.c.i |  | GUID Definition |  |  |  | III.B.3.c.i - Define and build Screen(s) for interfacing with the control tables to manage the meta data for the application
III.B.3.c.ii |  | Control Table Interface |  |  |  | III.B.3.c.ii - Oracle package to define the data management from the GUID in insert, update, and deleting(archiving) data in the metadata control tables
III.B.3.c.iii |  | Business rule management for BRM |  |  |  | III.B.3.c.iii - Business rule defintion for managing the BRM within the system
III.B.3.c.iv |  | Test Procedures to test BRM |  |  |  | III.B.3.c.iv - Test processes to fully test the BRM as it is being built , during testing, and deployment.
III.B.3.c.v |  | Documentation validation testing |  |  |  | III.B.3.c.v - Documentation of the validiation testing
III.B.3.d |  | Composer Structure |  |  |  | III.B.3.d - This is the structure for the building of the composers for each area. It is a template for building the routines that build routines.
III.B.3.d.i |  | Library Functions (common) |  |  |  | III.B.3.d.i - Understand the common Library functions needed and identify them for this process
III.B.3.d.ii |  | Library Functions (unique) |  |  |  | III.B.3.d.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.3.d.iii |  | Template defintion with detailed documentation |  |  |  | III.B.3.d.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.3.d.iv |  | Business Rules for Composer Level |  |  |  | III.B.3.d.iv - This section should define the business rules for the composer of processes. Ensuring that the controlled flow meets the security and business rules necessary for metadata development.
III.B.3.e |  | Composer Builder |  |  |  | III.B.3.e - This is a set of processes that build the processes for managing the data.
III.B.3.e.i |  | Library Functions (common) |  |  |  | III.B.3.e.i - Understand the common Library functions needed and identify them for this process
III.B.3.e.ii |  | Library Functions (unique) |  |  |  | III.B.3.e.ii - Understand the unique functions that will be needed to create this process, defining the functions and the common library they should be placed. The functions should be defined, a test plan for the function, and the function development as part of the template definition.
III.B.3.e.iii |  | Template defintion with detailed documentation |  |  |  | III.B.3.e.iii - This should be the complete template in the template format for a full defintion of each step and the calls and variables that need to be passed and recevied. This should include the common variable include file, plus the unique variables stored as meta data in the control tables.
III.B.3.e.iv |  | Business Rules for Composer Builder |  |  |  | III.B.3.e.iv - This section should define the business rules for the composer builder of composers. Ensuring that the controlled flow meets the security and business rules necessary for metadata development.
III.C |  | Test Defintion |  |  |  | III.C -
III.C.1 |  | Library Module Tests |  |  |  | III.C.1 - Tests plan to test each routine in the libraries to ensure that it functions as designed.
III.C.1.a |  | Define test requirements for each function |  |  |  | III.C.1.a - What is expected for each area
III.C.1.b |  | Define in / out bound test |  |  |  | III.C.1.b - define a set of test with correct inputs and incorrect inputs
III.C.1.c |  | Define exception test |  |  |  | III.C.1.c - define test to return exception not defined above
III.C.1.d |  | Define Null test |  |  |  | III.C.1.d - define null test and response
III.C.1.e |  | Define Query test |  |  |  | III.C.1.e - define query test if appropriate
III.C.2 |  | Control Table Tests |  |  |  | III.C.2 - Tests the data, constraints, and structure of the control tables to ensure they meets all requirements.
III.C.2.a |  | Define test requirements for each table |  |  |  | III.C.2.a - What is expected for each area
III.C.2.b |  | Define in / out bound test |  |  |  | III.C.2.b - define a set of test with correct inputs and incorrect inputs
III.C.2.c |  | Define exception test |  |  |  | III.C.2.c - define test to return exception not defined above
III.C.2.d |  | Define Null test |  |  |  | III.C.2.d - define null test and response
III.C.2.e |  | Define Query test |  |  |  | III.C.2.e - define query test if appropriate
III.C.3 |  | Business Rule Manager Test |  |  |  | III.C.3 - The business rule manager test system is a complete test suite of data, form, and use.
III.C.3.a |  | Define test requirements for each function |  |  |  | III.C.3.a - What is expected for each area
III.C.3.b |  | Define in / out bound test |  |  |  | III.C.3.b - define a set of test with correct inputs and incorrect inputs
III.C.3.c |  | Define exception test |  |  |  | III.C.3.c - define test to return exception not defined above
III.C.3.d |  | Define Null test |  |  |  | III.C.3.d - define null test and response
III.C.3.e |  | Define Query test |  |  |  | III.C.3.e - define query test if appropriate
III.C.3.f |  | Define test for control on each field on GUID |  |  |  | III.C.3.f - define tests for each GUID field control
III.C.3.g |  | Define test for in and out of range for each field |  |  |  | III.C.3.g - define tests for each GUID field control in and out of range
III.C.3.h |  | Define test for each control button on form |  |  |  | III.C.3.h - define test for each control button on screen
III.C.4 |  | Warehouse Manager Test |  |  |  | III.C.4 - The warehouse manager test tests all the procedures and functions that are involved witht the Warehouse manager package.
III.C.4.a |  | Define test requirements for each function or procedure in package |  |  |  | III.C.4.a - What is expected for each area
III.C.4.b |  | Define in / out bound test |  |  |  | III.C.4.b - define a set of test with correct inputs and incorrect inputs
III.C.4.c |  | Define exception test |  |  |  | III.C.4.c - define test to return exception not defined above
III.C.4.d |  | Define Null test |  |  |  | III.C.4.d - define null test and response
III.C.4.e |  | Define Query test |  |  |  | III.C.4.e - define query test if appropriate
III.C.4.f |  | Define test for each interaction between functions and procedures in package |  |  |  | III.C.4.f - define functional interaction tests
III.C.4.g |  | Define test for each cursor or query to database |  |  |  | III.C.4.g - define cursor and query tests
III.C.4.h |  | Define test for each exception defined in package |  |  |  | III.C.4.h - define tests to try each exception and expected error condition
III.C.5 |  | Composer Test |  |  |  | III.C.5 - These tests are designed to handle the composition of the composers and the component builders
III.C.5.a |  | Define test requirements for each function |  |  |  | III.C.5.a - What is expected for each area
III.C.5.b |  | Define in / out bound test |  |  |  | III.C.5.b - define a set of test with correct inputs and incorrect inputs
III.C.5.c |  | Define exception test |  |  |  | III.C.5.c - define test to return exception not defined above
III.C.5.d |  | Define Null test |  |  |  | III.C.5.d - define null test and response
III.C.5.e |  | Define Query test |  |  |  | III.C.5.e - define query test if appropriate
III.C.5.f |  | Define create and compile tests for exception handling |  |  |  | III.C.5.f - Define create and compile tests for exception handling
III.C.5.g |  | Define tests for each exception and control |  |  |  | III.C.5.g - Define tests for each exception and control
III.C.5.h |  | Define tests for execution of composer and execpted function |  |  |  | III.C.5.h - Define tests for execution of composer and execpted function
III.C.5.i |  | Define test for Perl Strict control |  |  |  | III.C.5.i - Define test for Perl Strict control
III.C.5.j |  | Define test for missing libraries |  |  |  | III.C.5.j - Define test for missing libraries
III.C.6 |  | Components Tests |  |  |  | III.C.6 - These tests are designed to test all the functionality of each of the components according to the business rules (meta data) that is defined in the control tables.
III.C.6.a |  | For each component test timer control |  |  |  | III.C.6.a - This tests the sleep timer algorithm for responsiveness
III.C.6.a.i |  | Forklift (FL) |  |  |  | III.C.6.a.i -
III.C.6.a.ii |  | Sorter (SO) |  |  |  | III.C.6.a.ii -
III.C.6.a.iii |  | Cataloger (CT) |  |  |  | III.C.6.a.iii -
III.C.6.a.iv |  | Stocker (ST) |  |  |  | III.C.6.a.iv -
III.C.6.a.v |  | Retriever (RT) |  |  |  | III.C.6.a.v -
III.C.6.a.vi |  | Packager (PR) |  |  |  | III.C.6.a.vi -
III.C.6.a.vii |  | Sender (SD) |  |  |  | III.C.6.a.vii -
III.C.6.b |  | For each component test each move file |  |  |  | III.C.6.b - This tests the permissions and access for moving files the module is responsible to move records.
III.C.6.b.i |  | Forklift (FL) |  |  |  | III.C.6.b.i -
III.C.6.b.ii |  | Sorter (SO) |  |  |  | III.C.6.b.ii -
III.C.6.b.iii |  | Cataloger (CT) |  |  |  | III.C.6.b.iii -
III.C.6.b.iv |  | Stocker (ST) |  |  |  | III.C.6.b.iv -
III.C.6.b.v |  | Retriever (RT) |  |  |  | III.C.6.b.v -
III.C.6.b.vi |  | Packager (PR) |  |  |  | III.C.6.b.vi -
III.C.6.b.vii |  | Sender (SD) |  |  |  | III.C.6.b.vii -
III.C.6.c |  | For each component test each library call |  |  |  | III.C.6.c - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.i |  | Forklift (FL) |  |  |  | III.C.6.c.i - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.ii |  | Sorter (SO) |  |  |  | III.C.6.c.ii - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.iii |  | Cataloger (CT) |  |  |  | III.C.6.c.iii - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.iv |  | Stocker (ST) |  |  |  | III.C.6.c.iv - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.v |  | Retriever (RT) |  |  |  | III.C.6.c.v - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.vi |  | Packager (PR) |  |  |  | III.C.6.c.vi - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.c.vii |  | Sender (SD) |  |  |  | III.C.6.c.vii - This tests each library call within a module, there will be several of these calls and each should be tested
III.C.6.d |  | For each component test each database call |  |  |  | III.C.6.d - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.i |  | Forklift (FL) |  |  |  | III.C.6.d.i - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.ii |  | Sorter (SO) |  |  |  | III.C.6.d.ii - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.iii |  | Cataloger (CT) |  |  |  | III.C.6.d.iii - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.iv |  | Stocker (ST) |  |  |  | III.C.6.d.iv - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.v |  | Retriever (RT) |  |  |  | III.C.6.d.v - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.vi |  | Packager (PR) |  |  |  | III.C.6.d.vi - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.d.vii |  | Sender (SD) |  |  |  | III.C.6.d.vii - Since most of the processes need to call the database to post or retrieve information in order to function, each call needs a test to ensure that the data passes cleanly.
III.C.6.e |  | For each component test each execute/system call |  |  |  | III.C.6.e - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.i |  | Forklift (FL) |  |  |  | III.C.6.e.i - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.ii |  | Sorter (SO) |  |  |  | III.C.6.e.ii - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.iii |  | Cataloger (CT) |  |  |  | III.C.6.e.iii - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.iv |  | Stocker (ST) |  |  |  | III.C.6.e.iv - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.v |  | Retriever (RT) |  |  |  | III.C.6.e.v - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.vi |  | Packager (PR) |  |  |  | III.C.6.e.vi - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.e.vii |  | Sender (SD) |  |  |  | III.C.6.e.vii - Since these modules will make calls to for commands to separate process each of these system calls will need to be tested.
III.C.6.f |  | For each component test compliation on creation |  |  |  | III.C.6.f - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.i |  | Forklift (FL) |  |  |  | III.C.6.f.i - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.ii |  | Sorter (SO) |  |  |  | III.C.6.f.ii - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.iii |  | Cataloger (CT) |  |  |  | III.C.6.f.iii - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.iv |  | Stocker (ST) |  |  |  | III.C.6.f.iv - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.v |  | Retriever (RT) |  |  |  | III.C.6.f.v - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.vi |  | Packager (PR) |  |  |  | III.C.6.f.vi - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.f.vii |  | Sender (SD) |  |  |  | III.C.6.f.vii - This tests when the process module is compiled or recompiled that all the permission that are needed are created and the compliation is correct. This will require the alteration of the control table data to test success and failure.
III.C.6.g |  | For each component test file/directory permissions |  |  |  | III.C.6.g - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.i |  | Forklift (FL) |  |  |  | III.C.6.g.i - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.ii |  | Sorter (SO) |  |  |  | III.C.6.g.ii - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.iii |  | Cataloger (CT) |  |  |  | III.C.6.g.iii - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.iv |  | Stocker (ST) |  |  |  | III.C.6.g.iv - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.v |  | Retriever (RT) |  |  |  | III.C.6.g.v - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.vi |  | Packager (PR) |  |  |  | III.C.6.g.vi - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.g.vii |  | Sender (SD) |  |  |  | III.C.6.g.vii - These tests should test all directory and file permissions needed by a process module to perform correctly.
III.C.6.h |  | TBD Tests |  |  |  | III.C.6.h -
III.C.6.i |  | TBD Tests |  |  |  | III.C.6.i -
III.C.6.j |  | TBD Tests |  |  |  | III.C.6.j -
III.C.6.l |  | TBD Tests |  |  |  | III.C.6.l -
III.C.7 |  | Integration Tests |  |  |  | III.C.7 - This is a suite of tests to test the Bulk warehouse management system from end to end.
III.C.7.a |  | FL - SO |  |  |  | III.C.7.a - This is a suite of tests that test the FL to the SO for each file type process thread
III.C.7.b |  | FL - WM |  |  |  | III.C.7.b - This is a suite of tests that test the FL to the WM for each file type process thread
III.C.7.c |  | SO - CT |  |  |  | III.C.7.c - This is a suite of tests that test the SO to the CT for each file type process thread
III.C.7.d |  | SO - WM |  |  |  | III.C.7.d - This is a suite of tests that tests the SO to the WM for each file type process thread
III.C.7.e |  | CT - ST |  |  |  | III.C.7.e - This is a suite of tests that tests the CT to the ST for each file type process thread
III.C.7.f |  | CT - WM |  |  |  | III.C.7.f - This is a suite of tests that tests the CT to the WM for each file type process thread
III.C.7.g |  | ST - WM |  |  |  | III.C.7.g - This is a suite of tests that tests the ST to the WM for each file type process thread
III.C.7.h |  | RT - PR |  |  |  | III.C.7.h - This is a suite of tests that tests the RT to the PR for each file type process thread
III.C.7.i |  | RT - WM |  |  |  | III.C.7.i - This is a suite of tests that test the RT to the WM for each file type process thread
III.C.7.j |  | PR - SD |  |  |  | III.C.7.j - This is a suite of tests that test the PR to the SD for each file type process thread
III.C.7.k |  | PR - WM |  |  |  | III.C.7.k - This is a suite of tests that test the PR to the WM for each file type process thread
III.C.7.l |  | END to END IN |  |  |  | III.C.7.l - This is a suite of tests that test the FL to ST and all the steps in between for each file type process. This is compliation of III.C.7.a through III.C.7.g
III.C.7.m |  | END to END OUT |  |  |  | III.C.7.m - This is a suite of tests that test the RT to the to the SD for each file type process thread. This is a compliation of III.C.7.h through III.C.7.k
III.C.7.n |  | TBD Tests |  |  |  | III.C.7.n -
III.C.7.o |  | TBD Tests |  |  |  | III.C.7.o -
III.C.7.p |  | TBD Tests |  |  |  | III.C.7.p -
III.D |  | Deployment Plan |  |  |  | III.D - This is the deployment plan that meets the specifications of LOGSA methodology and the needs of this project.
III.D.1 |  | Database Table and Metadata Deployment |  |  |  | III.D.1 - This is a standard method of deployment within the LOGSA Oracle databases
III.D.1.a |  | LOGSA Deployment Structure Setup |  |  |  | III.D.1.a -
III.D.1.a.i |  | Scripts for Tables |  |  |  | III.D.1.a.i - scripts to create tables
III.D.1.a.ii |  | Scripts for Packages |  |  |  | III.D.1.a.ii - scripts to create packages
III.D.1.a.iii |  | Scripts for Contraints |  |  |  | III.D.1.a.iii - scripts to create constraints
III.D.1.a.iv |  | Scripts for Indexes |  |  |  | III.D.1.a.iv - scripts to create indexes
III.D.1.a.v |  | Scripts for views |  |  |  | III.D.1.a.v - scripts to create views
III.D.1.a.vi |  | Scripts for sequences |  |  |  | III.D.1.a.vi - scripts to create sequences
III.D.1.a.vii |  | Scripts for synonyms |  |  |  | III.D.1.a.vii - scripts to create synonyms
III.D.1.a.viii |  | Scripts for data from each table |  |  |  | III.D.1.a.viii - scripts to load metadata for each control table
III.D.1.a.ix |  | TBD Scripts |  |  |  | III.D.1.a.ix -
III.D.2 |  | Application Deployment |  |  |  | III.D.2 - Since this is a n tier metadata based system the application deployment will be worked out with LOGSA current deployment teams.
III.D.2.a |  | Module Packaging |  |  |  | III.D.2.a - The packaging of the Composer Builder, Business manager GUID system, Directory Structure Creator, etc.
III.D.2.b |  | Metadata Packaging |  |  |  | III.D.2.b - Metadata packaging in XML format
III.D.2.c |  | Team Track Definition |  |  |  | III.D.2.c - Managing the Team Track steps
III.D.2.d |  | Module VM Check in |  |  |  | III.D.2.d - Check of all modules needed into VM
III.D.2.e |  | Metadata Packaging VM Check in |  |  |  | III.D.2.e - Check in packaging of metadata into VM
III.D.2.f |  | Deployment Test Suite VM Check in |  |  |  | III.D.2.f - Check in of Deployement Test Suite into VM
III.D.2.g |  | Documentation VM Check in |  |  |  | III.D.2.g - Check in of Documentation into VM
III.D.3 |  | In Place Deployment Test Suite |  |  |  | III.D.3 - This is a set of tests that tests the entire suite once it is in place in a production environment especially testing permissions, connectivity, and recreation on metadata changes.
III.D.3.a |  | Determine In Place Deployment Tests needed |  |  |  | III.D.3.a - Scripts to run the proper tests on the IN PLACE deployment of the Bulk Data manager system
III.D.3.b |  | Package Tests |  |  |  | III.D.3.b - The tests to handle the Packages
III.D.3.c |  | Test the package of test |  |  |  | III.D.3.c - The test that tests the package tests
III.D.3.d |  | Document the steps to run the test |  |  |  | III.D.3.d - Documentation of the steps to run the tests
III.D.3.e |  | Create the Deployment Test Suite |  |  |  | III.D.3.e - creation of the deployment test suite
IV. |  | Technical Signoff |  |  |  | IV. - This is the technical signoff
IV.A |  | Team |  |  |  | IV.A - Team signoff
IV.B |  | Management |  |  |  | IV.B - Management signoff
V. |  | Development Cycle |  |  |  | V. -
V.A. |  | Documentation |  |  |  | V.A. -
V.A.1 |  | System Documentation |  |  |  | V.A.1 - This documentation is for the overall system and should reflect the approved concept and design signed off by management
|  | Concept |  |  |  | - overall system all components
|  | Design Overview |  |  |  | - overall system all components
|  | Product Use |  |  |  | - overall system all components
|  | Control and Processing |  |  |  | - overall system all components
|  | Maintenance and Philosophy |  |  |  | - overall system all components
|  | Components and Definitions |  |  |  | - overall system all components
|  | Reference Appendixes |  |  |  | - overall system all components
V.A.2 |  | User Documentation |  |  |  | V.A.2 - This documentation is primarily the business rule manager part of the application, the detailed functionality of the composer builder, the composer builders, and the template concept of the functional processes.
|  | Concept |  |  |  | - User concept (executive level)
|  | Design Overview |  |  |  | - User concept (executive level)
|  | Product Use |  |  |  | - User concept (executive level)
|  | Control and Processing |  |  |  | - User concept (executive level)
|  | Maintenance and Philosophy |  |  |  | - User concept (executive level)
|  | Components and Definitions |  |  |  | - User concept (executive level)
|  | Reference Appendixes |  |  |  | - User concept (executive level)
V.A.3 |  | Test Documentation |  |  |  | V.A.3 - This is a compliation of the test plans and the testing process to ensure that all the components function as designed.
|  | Concept |  |  |  | - overall system all components
|  | Functional Description |  |  |  | - overall system all components
|  | Design |  |  |  | - overall system all components
|  | Structures and defintion |  |  |  | - overall system all components
|  | Reference Appendixes |  |  |  | - overall system all components
-
V.A.4 |  | Template Documentation |  |  |  | V.A.4 - This is the detailed documentation of the templates for the construction of each template and the reasoning behind the template design.
|  | Concept |  |  |  | - overall system all components
|  | Functional Description |  |  |  | - overall system all components
|  | Design |  |  |  | - overall system all components
|  | Structures and defintion |  |  |  | - overall system all components
|  | Reference Appendixes |  |  |  | - overall system all components
V.A.5 |  | Warehouse Manager Documentation |  |  |  | V.A.5 - The warehouse manager is the 'large' package that manages all the bulk file management that is passed and received between the bulk file management system and the CCBMWHER.
|  | Concept |  |  |  | - Warehouse Manager view
|  | Functional Description |  |  |  | - Warehouse Manager view
|  | Design |  |  |  | - Warehouse Manager view
|  | Calls and Access |  |  |  | - Warehouse Manager view
|  | Reference Appendixes |  |  |  | - Warehouse Manager view
V.B. |  | Test Development |  |  |  | V.B. -
V.B.1 |  | Library Module Tests |  |  |  | V.B.1 - These are the tests for the defined library modules
V.B.1.a |  | Database.pm |  |  |  | V.B.1.a - This library holds all the access and calls to the database and specifically the WM
V.B.1.b |  | Storage.pm |  |  |  | V.B.1.b - This library holds all the calls to move, store, retrieve a file in the Bulk Data Management System
V.B.1.c |  | Dataset.pm |  |  |  | V.B.1.c - This library holds all the calls to handle the data sets of information that must flow through the Bulk Data Management System
V.B.1.d |  | Plog.pm |  |  |  | V.B.1.d - This library hold all the calls that are specific to the PowerLOG-J application
V.B.1.e |  | CFD.pm |  |  |  | V.B.1.e - This library holds all the calls that are specific to manage the CFD files. Most of these calls will manage data and make Java/C++ calls to the CFD function library.
V.B.1.f |  | ComBld.pm |  |  |  | V.B.1.f - This library holds the calls for the Composer builder that are unique to the composer builder.
V.B.1.g |  | Composer.pm |  |  |  | V.B.1.g - This library holds the call that are unique to the composer modules the composer builder creates.
V.B.1.h |  | Sending.pm |  |  |  | V.B.1.h - This library is primarily used to send or receive files to a registered system through the SCP functionality.
V.B.1.i |  | Mail.pm |  |  |  | V.B.1.i - This library holds the calls to allow the application to send e-mail to the system or data requestors. This should include the ability to attach files to the mail message in the transfering of the data.
V.B.1.j |  | TBD |  |  |  | V.B.1.j -
V.B.2 |  | Control Table Tests |  |  |  | V.B.2 - These are the tests for the control tables.
V.B.3 |  | Business Rule Manager Test |  |  |  | V.B.3 - These are the tests for the Business Rule Manager
V.B.3.a |  | GUID |  |  |  | V.B.3.a - This set of tests cover every item on the GUID for full range of functionality
V.B.3.b |  | Database Calls |  |  |  | V.B.3.b - This set of tests cover all the calls to the database that the BRM makes and validates both the sending data and the results.
V.B.3.c |  | Security |  |  |  | V.B.3.c - This set of tests checks the security functions built into the application and ensures that they meet the desired level of security control. This is important with the BRM having the ability to insert code snippets into the control tables.
V.B.3.d |  | Insert |  |  |  | V.B.3.d - This set of tests validates the insertion of data into the control tables by the application to ensure that the data went in and can come out in the proper format.
V.B.3.e |  | Update |  |  |  | V.B.3.e - this set of tests validates the updating of the data in the control tables. This set also should test the archiving of the orginial data in the archiving tables for audit control.
V.B.3.f |  | Delete |  |  |  | V.B.3.f - This set of tests vaildates that archiving of the code on deletion of the data.
V.B.3.g |  | Reports |  |  |  | V.B.3.g - This set of tests should validate the reports the BRM presents back to the user.
V.B.3.h |  | Validation and Checking |  |  |  | V.B.3.h - This set of tests should stress the validationa and checking with especially care on potential harmful scripts values.
V.B.4 |  | Warehouse Manager Test |  |  |  | V.B.4 - These are the tests for the Warehouse manager
V.B.4.a |  | General Functions IN (I_) |  |  |  | V.B.4.a - These tests should test all the I_ functions to ensure they are handling data, throwing exceptions, and maintaining data integrity on all incoming data.
V.B.4.b |  | General Functions OUT (O_) |  |  |  | V.B.4.b - These tests should test all the O_ functions to ensure they are handling data, throwing exceptions, and maintaining data integrity on all out going data.
V.B.4.c |  | General Functions Data Management (D_) |  |  |  | V.B.4.c - These tests should stress the general functions in the WM package
V.B.4.d |  | CFD Functions (C_) |  |  |  | V.B.4.d - These tests should stress all the CFD functions in the package(s)
V.B.4.e |  | Plog Function (F_) |  |  |  | V.B.4.e - These tests should stress all the PowerLOG functions in the package(s)
V.B.4.f |  | TBD |  |  |  | V.B.4.f -
V.B.5 |  | Composer Test |  |  |  | V.B.5 - These are the tests for the Composer and Composer Builder
V.B.6 |  | Components Tests |  |  |  | V.B.6 - These are the tests for the components
V.B.7 |  | Integration Tests |  |  |  | V.B.7 - These are the integration tests
V.C |  | Library Module Development |  |  |  | V.C - This is the development section for the Library modules
V.C.1 |  | Database.pm |  |  |  | V.C.1 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
V.C.2 |  | Storage.pm |  |  |  | V.C.2 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
V.C.3 |  | Dataset.pm |  |  |  | V.C.3 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
-
V.C.4 |  | Plog.pm |  |  |  | V.C.4 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
-
V.C.5 |  | CFD.pm |  |  |  | V.C.5 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
-
V.C.6 |  | ComBld.pm |  |  |  | V.C.6 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
-
V.C.7 |  | Composer.pm |  |  |  | V.C.7 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
-
V.C.8 |  | Sending.pm |  |  |  | V.C.8 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
-
V.C.9 |  | Mail.pm |  |  |  | V.C.9 -
|  | Define all functions |  |  |  | -
|  | Build test to test each function |  |  |  | -
|  | Create each function |  |  |  | -
|  | Determine the use of functions in other libraries |  |  |  | -
|  | Document each function for IN/OUT function |  |  |  | -
V.D |  | Template Development |  |  |  | V.D - This is the development section for the Template creation and defintion
V.D.1 |  | Forklift (FL) |  |  |  | V.D.1 -
V.D.1.a |  | Header Section |  |  |  | V.D.1.a - Standard header section for all processes
V.D.1.b |  | Variables |  |  |  | V.D.1.b - Common variables used by all processes with unique variables attached on end
V.D.1.c |  | Top Timer Loop |  |  |  | V.D.1.c - Standard top timer loop for all processes
V.D.1.d |  | File check |  |  |  | V.D.1.d - Standard file check routine for all processes
V.D.1.e |  | Top Process Section |  |  |  | V.D.1.e - Standard top process section for all forklift processes
V.D.1.f |  | Processes |  |  |  | V.D.1.f - The area where the specific paragraphs for this process are located
V.D.1.g |  | Bottom Process Section |  |  |  | V.D.1.g - Standard bottom process section for all forklift processes
V.D.1.h |  | Bottom Timer Loop |  |  |  | V.D.1.h - Standard bottom timer loop for all processes
V.D.1.i |  | Close Section |  |  |  | V.D.1.i - Standard close section and exception handling for all processes
V.D.2 |  | Sorter (SO) |  |  |  | V.D.2 -
V.D.2.a |  | Header Section |  |  |  | V.D.2.a - Standard header section for all processes
V.D.2.b |  | Variables |  |  |  | V.D.2.b - Common variables used by all processes with unique variables attached on end
V.D.2.c |  | Top Timer Loop |  |  |  | V.D.2.c - Standard top timer loop for all processes
V.D.2.d |  | File check |  |  |  | V.D.2.d - Standard file check routine for all processes
V.D.2.e |  | Top Process Section |  |  |  | V.D.2.e - Standard top process section for all sorter processes
V.D.2.f |  | Processes |  |  |  | V.D.2.f - The area where the specific paragraphs for this process are located
V.D.2.g |  | Bottom Process Section |  |  |  | V.D.2.g - Standard bottom process section for all sorter processes
V.D.2.h |  | Bottom Timer Loop |  |  |  | V.D.2.h - Standard bottom timer loop for all processes
V.D.2.i |  | Close Section |  |  |  | V.D.2.i - Standard close section and exception handling for all processes
V.D.3 |  | Cataloger (CT) |  |  |  | V.D.3 -
V.D.3.a |  | Header Section |  |  |  | V.D.3.a - Standard header section for all processes
V.D.3.b |  | Variables |  |  |  | V.D.3.b - Common variables used by all processes with unique variables attached on end
V.D.3.c |  | Top Timer Loop |  |  |  | V.D.3.c - Standard top timer loop for all processes
V.D.3.d |  | File check |  |  |  | V.D.3.d - Standard file check routine for all processes
V.D.3.e |  | Top Process Section |  |  |  | V.D.3.e - Standard top process section for all cataloger processes
V.D.3.f |  | Processes |  |  |  | V.D.3.f - The area where the specific paragraphs for this process are located
V.D.3.g |  | Bottom Process Section |  |  |  | V.D.3.g - Standard bottom process section for all cataloger processes
V.D.3.h |  | Bottom Timer Loop |  |  |  | V.D.3.h - Standard bottom timer loop for all processes
V.D.3.i |  | Close Section |  |  |  | V.D.3.i - Standard close section and exception handling for all processes
V.D.4 |  | Stocker (ST) |  |  |  | V.D.4 -
V.D.4.a |  | Header Section |  |  |  | V.D.4.a - Standard header section for all processes
V.D.4.b |  | Variables |  |  |  | V.D.4.b - Common variables used by all processes with unique variables attached on end
V.D.4.c |  | Top Timer Loop |  |  |  | V.D.4.c - Standard top timer loop for all processes
V.D.4.d |  | File check |  |  |  | V.D.4.d - Standard file check routine for all processes
V.D.4.e |  | Top Process Section |  |  |  | V.D.4.e - Standard top process section for all stocker processes
V.D.4.f |  | Processes |  |  |  | V.D.4.f - The area where the specific paragraphs for this process are located
V.D.4.g |  | Bottom Process Section |  |  |  | V.D.4.g - Standard bottom process section for all stocker processes
V.D.4.h |  | Bottom Timer Loop |  |  |  | V.D.4.h - Standard bottom timer loop for all processes
V.D.4.i |  | Close Section |  |  |  | V.D.4.i - Standard close section and exception handling for all processes
V.D.5 |  | Retriever (RT) |  |  |  | V.D.5 -
V.D.5.a |  | Header Section |  |  |  | V.D.5.a - Standard header section for all processes
V.D.5.b |  | Variables |  |  |  | V.D.5.b - Common variables used by all processes with unique variables attached on end
V.D.5.c |  | Top Timer Loop |  |  |  | V.D.5.c - Standard top timer loop for all processes
V.D.5.d |  | File check |  |  |  | V.D.5.d - Standard file check routine for all processes
V.D.5.e |  | Top Process Section |  |  |  | V.D.5.e - Standard top process section for all retriever processes
V.D.5.f |  | Processes |  |  |  | V.D.5.f - The area where the specific paragraphs for this process are located
V.D.5.g |  | Bottom Process Section |  |  |  | V.D.5.g - Standard bottom process section for all retriever processes
V.D.5.h |  | Bottom Timer Loop |  |  |  | V.D.5.h - Standard bottom timer loop for all processes
V.D.5.i |  | Close Section |  |  |  | V.D.5.i - Standard close section and exception handling for all processes
V.D.6 |  | Packager (PR) |  |  |  | V.D.6 -
V.D.6.a |  | Header Section |  |  |  | V.D.6.a - Standard header section for all processes
V.D.6.b |  | Variables |  |  |  | V.D.6.b - Common variables used by all processes with unique variables attached on end
V.D.6.c |  | Top Timer Loop |  |  |  | V.D.6.c - Standard top timer loop for all processes
V.D.6.d |  | File check |  |  |  | V.D.6.d - Standard file check routine for all processes
V.D.6.e |  | Top Process Section |  |  |  | V.D.6.e - Standard top process section for all packager processes
V.D.6.f |  | Processes |  |  |  | V.D.6.f - The area where the specific paragraphs for this process are located
V.D.6.g |  | Bottom Process Section |  |  |  | V.D.6.g - Standard bottom process section for all packager processes
V.D.6.h |  | Bottom Timer Loop |  |  |  | V.D.6.h - Standard bottom timer loop for all processes
V.D.6.i |  | Close Section |  |  |  | V.D.6.i - Standard close section and exception handling for all processes
V.D.7 |  | Sender (SD) |  |  |  | V.D.7 -
V.D.7.a |  | Header Section |  |  |  | V.D.7.a - Standard header section for all processes
V.D.7.b |  | Variables |  |  |  | V.D.7.b - Common variables used by all processes with unique variables attached on end
V.D.7.c |  | Top Timer Loop |  |  |  | V.D.7.c - Standard top timer loop for all processes
V.D.7.d |  | File check |  |  |  | V.D.7.d - Standard file check routine for all processes
V.D.7.e |  | Top Process Section |  |  |  | V.D.7.e - Standard top process section for all sender processes
V.D.7.f |  | Processes |  |  |  | V.D.7.f - The area where the specific paragraphs for this process are located
V.D.7.g |  | Bottom Process Section |  |  |  | V.D.7.g - Standard bottom process section for all sender processes
V.D.7.h |  | Bottom Timer Loop |  |  |  | V.D.7.h - Standard bottom timer loop for all processes
V.D.7.i |  | Close Section |  |  |  | V.D.7.i - Standard close section and exception handling for all processes
V.E |  | Control Table Development |  |  |  | V.E - This is the development section for the Control Tables.
V.E.1 |  | Control Table Structure and Constraints |  |  |  | V.E.1 - This is the development section for the control tables structure and constraint definition
V.E.2 |  | Metadata for the Control Table |  |  |  | V.E.2 - This is the data and code snippets that are used to construct and control the code that is built
V.E.2.a |  | Common Library Paragraphs |  |  |  | V.E.2.a - These are the common Library calls paragraphs using the common variable arrays to capture the data
V.E.2.b |  | Common Variable Paragraphs |  |  |  | V.E.2.b - These are the common variable lists used in all processes
V.E.2.c |  | Common Timer Paragraphs |  |  |  | V.E.2.c - These are the standard timer paragraphs used in the processes
V.E.2.d |  | Common Header Paragraphs |  |  |  | V.E.2.d - These are the common header paragraphs used in all processes
V.E.2.e |  | Forklift (FL) Process Paragraphs |  |  |  | V.E.2.e - These are the specific paragraphs used for the forklift processes
V.E.2.f |  | Sorter (SO)Process Paragraphs |  |  |  | V.E.2.f - These are the specific paragraphs used for the sorter processes
V.E.2.g |  | Cataloger (CT)Process Paragraphs |  |  |  | V.E.2.g - These are the specific paragraphs used for the cataloger processes
V.E.2.h |  | Stocker (ST)Process Paragraphs |  |  |  | V.E.2.h - These are the specific paragraphs used for the stocker processes
V.E.2.i |  | Retriever (RT)Process Paragraphs |  |  |  | V.E.2.i - These are the specific paragraphs used for the retriever processes
V.E.2.j |  | Packager (PR)Process Paragraphs |  |  |  | V.E.2.j - These are the specific paragraphs used for the paackager processes
V.E.2.k |  | Sender (SD)Process Paragraphs |  |  |  | V.E.2.k - These are the specific paragraphs used for the sender processes
V.E.2.l |  | Composer Builder Paragraphs |  |  |  | V.E.2.l - These are the paragraphs that the composer builder uses to build the composers
V.E.2.m |  | Composer Paragraphs |  |  |  | V.E.2.m - These are the composer paragraphs that are used to build the processes
V.E.2.n |  | CFD Paragraphs |  |  |  | V.E.2.n - These are the paragraphs that handle the CFD file management
V.E.2.o |  | PowerLOG Paragraphs |  |  |  | V.E.2.o - These are the paragraphs that handle the PowerLOG file management
V.E.2.p |  | Other Metadata |  |  |  | V.E.2.p - These are the other Metadata paragraphs that do not fall in the above sections
V.F |  | Composer Builder |  |  |  | V.F -
V.F.1 |  | Composer Template |  |  |  | V.F.1 - This is the development of the composer template that the composer builder will use to create the necessary composers for the various functions
V.F.1.a |  | Header Section |  |  |  | V.F.1.a - The section to declare the global perl info stuff
V.F.1.b |  | Variables |  |  |  | V.F.1.b - The standard variables used in all code
V.F.1.c |  | Template Loader |  |  |  | V.F.1.c - The section that loads the template of the process to be created
V.F.1.d |  | Control Table Load |  |  |  | V.F.1.d - The section that loads the metadata from the control tables through the WM for building the process
V.F.1.e |  | Top Process Build Loop |  |  |  | V.F.1.e - The top of the process loop
V.F.1.f |  | Build construction paragraphs |  |  |  | V.F.1.f - The section that adds the paragraphs necessary for the process to perform its task
V.F.1.g |  | Bottom Process Section |  |  |  | V.F.1.g - The bottom of the process section
V.F.1.h |  | Close Section |  |  |  | V.F.1.h - The close and exception section
V.F.2 |  | Composer Builder |  |  |  | V.F.2 - This is the program that will build the composers. This development along with the warehouse manager and libraries are the three keys pieces of code that will generate all the other components
V.F.2.a |  | Composer Builder Detailed Design and Philosophy |  |  |  | V.F.2.a - The concept of a program that builds programs to build programs seems a little extreme, but since all the processes have the same basic structure and rules and differ only in the definition of the file type(s) they are actually processing this leads to a good arguement to build one module that can build the modules that build the final processes. The construction of the sub modules or processes are based off of templates designed for each level.
V.F.2.b |  | Composer Builder Structure |  |  |  | V.F.2.b - This is the structure of the Composer Builder and should be built, reviewed and agreed that it will with its library and metadata build the modules that will build the actual processes that move and manage the incoming files and their long term storage.
V.F.2.c |  | Composer Builder Library |  |  |  | V.F.2.c - This library will contain components that do not exist in the the common libraries of the overall system. It will highly use the database, the file management, string parsing, file building libraries that will be common to all the processes. There however will be components that only exist for the composer builder and should go in this library.
V.F.2.d |  | Composer Builder Metadata |  |  |  | V.F.2.d - The metadata is more than values. It will include code snippets that are defined as paragraphs. Paragraphs will contain comments that explain exactly what they are to do and the common and uncommon variables that are required for them to function properly. Each paragraph should handle its own exceptions and leave all results within the process or module in common structures for further handling by other paragraphs within the module/process.
V.F.2.e |  | Composer Builder Compiler Script |  |  |  | V.F.2.e - Since the Composer builder will be a compiled process the controls for the compilation need to be fully defined.
V.F.2.f |  | Composer Builder exception and valiation Section |  |  |  | V.F.2.f - There are some overall handling of the exceptions and the validation of the metadata that exist in the in the construction of the composers. These exception handlers should handle proper error messaging back to the compiling function to fully explain the error and NOT replace the existing code
V.F.3 |  | Composer |  |  |  | V.F.3 - Composer is the Perl Procedures that are the result of the composer builder for each process type and function
V.F.3.a |  | Composer Template Development |  |  |  | V.F.3.a - Since the composers will all have the same look and feel a standard template of the structure of the code is possible.
V.F.3.b |  | Composer Library Development |  |  |  | V.F.3.b - The composer library development should work in concert with the composer builder and all components that a composer builds. However there will be a few functions that will be strictly composer and those paragraphs should go into the composer library.
V.F.3.c |  | Composer Metadata Development |  |  |  | V.F.3.c - The composer library development should work in concert with the composer builder and all components that a composer builds. However there will be a few paragraphs and variable constructions that will be strictly composer and those paragraphs should go into the composer library.
V.F.3.d |  | Composer Compiler Script Development |  |  |  | V.F.3.d - Since the composers can be rebuild as needed to redefine the modules/processes that they build the compiler script needs to handle controls and permission as well as the exception handling the the case of errors in the compliation.
V.F.4 |  | Composer Control |  |  |  | V.F.4 - This is the program that will manage the control of the composers and the recomposition in the event of a change in the control tables through the business rule manager or an evolution of the processes in concurrent testing and control
V.G |  | Phase One Integration |  |  |  | V.G - This is the first stage of the integration of the various components
V.G.1 |  | Control Table Data Definition |  |  |  | V.G.1 - The control table and business rule manager are linked with the library control table interface
V.G.2 |  | Library Control Table Interface |  |  |  | V.G.2 - The library control interface are linked with the business rule manager and tested for completeness
V.G.3 |  | Warehouse Manager |  |  |  | V.G.3 - Oracle pacakge interface for all Bulk Data modules/processes
V.G.3.a |  | General Functions IN (I_) |  |  |  | V.G.3.a - These are the general functions that handle data into the package. These include the standard parsers, redirectors, etc.
V.G.3.b |  | General Functions OUT (O_) |  |  |  | V.G.3.b - These are the general functions that handle the out bound data from the packages to the modules and processes fo the Bulk Data Management System.
V.G.3.c |  | General Functions Data Management (D_) |  |  |  | V.G.3.c - These are the data management functions that take arrays of data that has been received and works with the data to putting or retrieving it from the correct locations
V.G.3.d |  | CFD Functions (C_) |  |  |  | V.G.3.d - These are the specific functions for managing the data that is passed in or out for the CFD function (ABCD files)
V.G.3.e |  | Plog Function (F_) |  |  |  | V.G.3.e - These are the specific functions for managing the data that is passed in or out for the PowerLOG files (all types)
V.G.3.f |  | TBD Functions |  |  |  | V.G.3.f -
V.H |  | Phase Two Integration |  |  |  | V.H - The second stage of integration is the linking and testing of the composer builder with all the library functions
V.H.1 |  | Composer Builder |  |  |  | V.H.1 - The composer builder is merged in to the libraries and control tables for processing
V.H.2 |  | Composer Builder Library Interface |  |  |  | V.H.2 - The libraries are linked in with the composer builder.
V.I |  | Phase Three Process Building |  |  |  | V.I - The third stage will actually build the composers for each of the various templates
V.I.1 |  | Metadata defintion for Each Template Defintion |  |  |  | V.I.1 - The metadata defintion of each template type will be defined and entered in the control tables and libraries
V.I.2 |  | Composer Metadata merge |  |  |  | V.I.2 - The Composer metadata with the composer templates will be merged for a working composer.
V.J |  | Phase Four Component Integration |  |  |  | V.J - This is the stage where the final modules (Perl Programs) will be created from the control tables, libraries and composers for each function type.
V.J.1 |  | Forklift |  |  |  | V.J.1 - The forklift process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.J.2 |  | Sorter |  |  |  | V.J.2 - The sorter process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.J.3 |  | Cataloger |  |  |  | V.J.3 - The cataloger process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.J.4 |  | Stocker |  |  |  | V.J.4 - The stocker process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.J.5 |  | Retriever |  |  |  | V.J.5 - The retriever process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.J.6 |  | Packager |  |  |  | V.J.6 - The packager process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.J.7 |  | Sender |  |  |  | V.J.7 - The sender process will be built and tested using the control tables, libraries, and forklift template using the composer processes created in initial development.
V.K |  | Deployment Plan |  |  |  | V.K - This is the development of the deployment plan for moving the applications and data to the production CCBMWHER
V.K.1 |  | Database Table and Metadata Deployment |  |  |  | V.K.1 - This is the placement and building of all the Oracle components and metadata that has been developed.
V.K.2 |  | Application Deployment |  |  |  | V.K.2 - This the the packaging and deployment plan for the application modules and directory structure
V.K.3 |  | In Place Deployment Test Suite |  |  |  | V.K.3 - This is the in place deployment test suite that will include all the previous tests plus tests on permissions, metadata replacement, and the entire functional process
VI. |  | Development Testing Cycle |  |  |  | VI. - With each phase in the development cycle there is a test suite that will be developed and run against the application
VI.A |  | Phase One |  |  |  | VI.A - This is phase one test development
VI.A.1 |  | Library Module Tests |  |  |  | VI.A.1 - These tests will test each subroutine in the each library and will be designed to do regression testing on the evolution of the libraries.
VI.A.2 |  | Control Table Tests |  |  |  | VI.A.2 - These tests will test each of the control tables and the validity of the data and code snippets that will reside in the tables as defined by the business rule manager.
VI.A.3 |  | Business Rule Manager Test |  |  |  | VI.A.3 - The business rule manager tests are test to work each area of the business manager and ensure that all of the functions in the business manager will control the data and metadata to the point of trapping out errors from being entered into the control tables.
VI.A.4 |  | Warehouse Manager Test |  |  |  | VI.A.4 - The warehouse manager with its control of moving data and controls between the warehouse and the bulk management system will need each function and procedure fully tested to ensure that all information passed is correct.
VI.B |  | Phase Two |  |  |  | VI.B - The phase two tests are designed primarily toward the Composer and Composer builder.
VI.B.1 |  | Composer Test |  |  |  | VI.B.1 - The composer and composer builder tests shoulld stress test the applications and the templates, metadata, libraries, and communication between the Perl applications and the warehouse manager in its passing of information.
VI.C |  | Phase Three |  |  |  | VI.C - This phase tests the results (the dynamically built processes)
VI.C.1 |  | Components Tests |  |  |  | VI.C.1 - This tests the components that are built with the composer builder and the composers.
VI.D |  | Phase Four |  |  |  | VI.D - This is the full integration tests
VI.D.1 |  | Integration Tests |  |  |  | VI.D.1 - Each of these tests test the integration of the processes and their ability to work in concert and perform the overall tasks that the bulk data management system is proposed to handle.
VII. |  | Functional Testing Cycle |  |  |  | VII. - There is a set of functional tests that will be run independent of development to ensure that the application does what it is suppose to do. The phases are the same as the development and some can be run in an offset concurrence with the development.
VII.A |  | Phase One |  |  |  | VII.A - Testing of the base control components
VII.A.1 |  | Library Module Tests |  |  |  | VII.A.1 - Library module testing
VII.A.2 |  | Control Table Tests |  |  |  | VII.A.2 - Control table testing
VII.A.3 |  | Business Rule Manager Test |  |  |  | VII.A.3 - business rule manager testing
VII.A.4 |  | Warehouse Manager Test |  |  |  | VII.A.4 - warehouse manager testing
VII.B |  | Phase Two |  |  |  | VII.B - Phase two is the composer builder/composer testing
VII.B.1 |  | Composer Test |  |  |  | VII.B.1 - Composer tests will be run with the individual result sets tested for completeness and functionality.
VII.C |  | Phase Three |  |  |  | VII.C - Phase three will be run concurrently with phase two to ensure that the components built in phase two will fully function and perform the tasks they were built to do.
VII.C.1 |  | Components Tests |  |  |  | VII.C.1 - Each component in the template set will be fully tested for each of the various types of files that they will need to process and ensure that their processing is correct and complete.
VII.D |  | Phase Four |  |  |  | VII.D - This is the final phase of testing
VII.D.1 |  | Integration Tests |  |  |  | VII.D.1 - This fully tests all the integration of each of the modules and ensures that all the processes are working and handing off to the proper follow process the correction and complete data set and information.
VIII. |  | Move from Test Environment |  |  |  | VIII. - When testing is complete and signed off by the testers the packaging of the components up for deployment will begin.
VIII.A |  | Package for Deployment |  |  |  | VIII.A - As defined the entire system will be packaged for deployment
VIII.B |  | Submit for Move |  |  |  | VIII.B - This will follow the LOGSA defined methods for submitting the entire application for movement to production
VIII.C |  | Run Development Test Suite |  |  |  | VIII.C - When deployed the entire development test suite will be run against the application to make sure that no component fails to perform the planned and tested functionality.
IX. |  | Process Signoff |  |  |  | IX. - The process will be signed off
IX.A |  | Acceptance Signoff |  |  |  | IX.A - The acceptance signoff by the management and development team will take place upon the passing of the Test Suite on the deployed application
IX.B |  | Lessons Learned |  |  |  | IX.B - The lessons learned and the things that can be done better will be documented and the plan for long term maintenance will be defined.
IX.C |  | Deliver Final Documentation |  |  |  | IX.C - The documention will go through a final edit and be submitted as a complete package.