## Middle A Schedule
1. The lessons learned from our Fielding Group 1 taught us that he most difficult part of a Cutover is all of the Financial dependencies. As a result, our earlier plan to field every 2 weeks is not executable. We Changed that strategy to doing a Cutover every 4 weeks. 2. After Fielding Group 8, the specific units listed for a Fielding Group are for ACOM/ASC/DRU allocation purposes only. For instance, whiel specific states for the ARNG are listed in July 13, the ARNG is free to place any ARNG fielding effort within that allocation. We recognize that the movements from previous schedules will require some hard staff work to check unit availability, etc. This schedule reflects our best estimate of what the level of effort we are capable of producing while ensuring we do fielding right..no drive by fieldings.
COMMAND | RIC | UNIT | LOO | CONTROLLING CTASC | UIC | DODAAC | LOCATION | TYPE SSA (PER CTASC) | TYPE SITE | FIELDING (BLACKOUT DATE) | FIELDING GROUP | D-180 | Adv LU Trg - (D-160) | D-120 | D-90 | D-60 | D-30
ARNG | A66 | VAARNG SUPPLY AND SE | National Guard | ARNG | W7N5AA | W26L8F | VA NG | 3 | Tactical | 2012-11-08 | 1 | 2012-05-11 | 2012-05-29 | 2012-07-11 | 2012-08-10 | 2012-09-07 | 2012-10-09
ASC | AXJ | DOL FT LEE | Active - CONUS | ASC_E | W6CPAA | W26ADX | LEE | 7 | Non-Tactical | 2012-11-08 | 1 | 2012-05-11 | 2012-05-29 | 2012-07-11 | 2012-08-10 | 2012-09-07 | 2012-10-09
USARC | WXU | 87TH DIV USARC SARSS | Reserve | USARC | W86MAA | W906DJ | DRC | 3 | Tactical | 2012-11-08 | 1 | 2012-05-11 | 2012-05-29 | 2012-07-11 | 2012-08-10 | 2012-09-07 | 2012-10-09
USARC | WXU | 85TH DIV USARC SARSS | Reserve | USARC | W86MAA | W906DJ | DRC | 3 | Tactical | 2012-11-08 | 1 | 2012-05-11 | 2012-05-29 | 2012-07-11 | 2012-08-10 | 2012-09-07 | 2012-10-09
USARC | WXW | 335 TSB | Reserve | USARC | WNEUR1 | W906CR | DRC | 3 | Tactical | 2012-11-08 | 1 | 2012-05-11 | 2012-05-29 | 2012-07-11 | 2012-08-10 | 2012-09-07 | 2012-10-09
ARNG | A13 | USPFO FOR ALABAMA | National Guard | ARNG | W7MTAA | W31LPY | AL NG | 3 | Tactical | 2013-02-20 | 3 | 2012-08-24 | 2012-09-11 | 2012-10-23 | 2012-11-22 | 2012-12-21 | 2013-01-21
ASC | AXK | AP HILL SUP SS | Active - CONUS | ASC_E | W2LQAA | W26DJS | AP HILL | 7 | Non-Tactical | 2013-02-20 | 3 | 2012-08-24 | 2012-09-11 | 2012-10-23 | 2012-11-22 | 2012-12-21 | 2013-01-21
ASC | AXG | FT MYER SARSS1 | Active - CONUS | ASC_E | W0UC06 | W73BF0 | MYER | 7 | Non-Tactical | 2013-02-20 | 3 | 2012-08-24 | 2012-09-11 | 2012-10-23 | 2012-11-22 | 2012-12-21 | 2013-01-21
ARNG | A32 | USPFO FOR KENTUCKY | National Guard | ARNG | W7NAAA | W81K70 | KY NG | 3 | Tactical | 2013-02-20 | 3 | 2012-08-24 | 2012-09-11 | 2012-10-23 | 2012-11-22 | 2012-12-21 | 2013-01-21
ARNG | WGP | USPFO NORTH CAROLINA | National Guard | ARNG | W7NS01 | W81KDP | NC NG | 3 | Tactical | 2013-03-20 | 4 | 2012-09-21 | 2012-10-09 | 2012-11-20 | 2012-12-20 | 2013-01-18 | 2013-02-18
ARNG | A29 | USPFO-IOWA WH # 12 | National Guard | ARNG | W7M8AA | W81JM8 | IA NG | 3 | Tactical | 2013-03-20 | 4 | 2012-09-21 | 2012-10-09 | 2012-11-20 | 2012-12-20 | 2013-01-18 | 2013-02-18
ARNG | WCF | NATL MAINT TNG CENTE | National Guard | ARNG | W7AAAA | W90ALW | IA NG | 3 | Tactical | 2013-03-20 | 4 | 2012-09-21 | 2012-10-09 | 2012-11-20 | 2012-12-20 | 2013-01-18 | 2013-02-18
FORSCOM | WAM | ACO 307TH BSB 1BCT | Active - CONUS | ASC_E | WABHA0 | W36LKG | BRAGG | 3 | Tactical | 2013-04-17 | 5 | 2012-10-19 | 2012-11-06 | 2012-12-18 | 2013-01-17 | 2013-02-15 | 2013-03-18
FORSCOM | WAU | ACO 122D ASB 82 CAB | Active - CONUS | ASC_E | WDJXA0 | W36N0T | BRAGG | 3 | Tactical | 2013-04-17 | 5 | 2012-10-19 | 2012-11-06 | 2012-12-18 | 2013-01-17 | 2013-02-15 | 2013-03-18
FORSCOM | WCN | 188 DIST CO BDB | Active - CONUS | ASC_E | WDEKA0 | W904H6 | BRAGG | 3 | Tactical | 2013-05-15 | 6 | 2012-11-16 | 2012-12-04 | 2013-01-15 | 2013-02-14 | 2013-03-15 | 2013-04-15
FORSCOM | WAH | 364TH S &S CO | Active - CONUS | ASC_E | WEYK02 | W36GKH | BRAGG | 3 | Tactical | 2013-05-15 | 6 | 2012-11-16 | 2012-12-04 | 2013-01-15 | 2013-02-14 | 2013-03-15 | 2013-04-15
FORSCOM | W6T | 249 QM CO | Active-CONUS | ASC_E | WE3CAA | W8002S | BRAGG | 3 | Tactical | 2013-05-15 | 6 | 2012-11-16 | 2012-12-04 | 2013-01-15 | 2013-02-14 | 2013-03-15 | 2013-04-15
ASC | AXP | FT MEADE SARSS1 | Active - CONUS | ASC_E | W0US39 | W23A71 | MEADE | 7 | Non-Tactical | 2013-06-12 | 7 | 2012-12-14 | 2013-01-01 | 2013-02-12 | 2013-03-14 | 2013-04-12 | 2013-05-13
ARNG | A46 | USPFO FOR NH WHSE SA | National Guard | ARNG | W7NN01 | W14UL3 | NH NG | 3 | Tactical | 2013-06-12 | 7 | 2012-12-14 | 2013-01-01 | 2013-02-12 | 2013-03-14 | 2013-04-12 | 2013-05-13
ARNG | A21 | USPFO FOR DELAWARE | National Guard | ARNG | W7M0AA | W81J8X | DE NG | 3 | Tactical | 2013-06-12 | 7 | 2012-12-14 | 2013-01-01 | 2013-02-12 | 2013-03-14 | 2013-04-12 | 2013-05-13
ARNG | A62 | USPFO FOR TN (SARSS1 | National Guard | ARNG | W7N1AA | W81JND | TN NG | 3 | Tactical | 2013-06-12 | 7 | 2012-12-14 | 2013-01-01 | 2013-02-12 | 2013-03-14 | 2013-04-12 | 2013-05-13
ASC | AGU | DOL SSA | Active - CONUS | ASC_E | WOU34B | W81YT4 | BRAGG | 7 | Non-Tactical | 2013-07-17 | 8 | 2013-01-18 | 2013-02-05 | 2013-03-19 | 2013-04-18 | 2013-05-17 | 2013-06-17
ARNG | A48 | USPFO FOR NJARNG | National Guard | ARNG | W7NPAA | W81KR3 | NJ NG | 3 | Non-Tactical | 2013-07-17 | 8 | 2013-01-18 | 2013-02-05 | 2013-03-19 | 2013-04-18 | 2013-05-17 | 2013-06-17
ARNG | A59 | USPFO FOR RHODE ISLA | National Guard | ARNG | W7NYAA | W17S13 | RI NG | 3 | Non-Tactical | 2013-07-17 | 8 | 2013-01-18 | 2013-02-05 | 2013-03-19 | 2013-04-18 | 2013-05-17 | 2013-06-17
ARNG | A36 | USPFO FOR MD WHS S-1 | National Guard | ARNG | W7NDAA | W23R7B | MD NG | 3 | Non-Tactical | 2013-07-17 | 8 | 2013-01-18 | 2013-02-05 | 2013-03-19 | 2013-04-18 | 2013-05-17 | 2013-06-17
ARNG | A65 | USPFO VERMONT SARSS1 | National Guard | ARNG | W7N4AA | W81KBL | VT NG | 3 | Non-Tactical | 2013-07-17 | 8 | 2013-01-18 | 2013-02-05 | 2013-03-19 | 2013-04-18 | 2013-05-17 | 2013-06-17
ARNG | A61 | USPFO FOR SOUTH CAROLINA | National Guard | ARNG | W7NZ01 | W37U1D | SC NG | 3 | Non-Tactical | 2013-07-17 | 8 | 2013-01-18 | 2013-02-05 | 2013-03-19 | 2013-04-18 | 2013-05-17 | 2013-06-17
USARC | WPU | 84 TNG CMD (UR) | Reserve | USARC | WYAEAA | W90T5U | BRAGG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
USARC | WPU | 80th TASS | Reserve | USARC | WYAEAA | W90T5U | BRAGG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
USARC | WPU | 108th CMD (IET) | Reserve | USARC | WYAEAA | W90T5U | BRAGG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
USARC | WPU | 75th MCTD | Reserve | USARC | WYAEAA | W90T5U | BRAGG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
USARC | WPU | ARRTC | Reserve | USARC | WYAEAA | W90T5U | BRAGG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
ARNG | A78 | 1108TH AVCRAD SARSS1 | National Guard | ARNG | W7TNAA | W90AUA | MS NG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
ARNG | W0C | MSARNG AVCRAD | National Guard | ARNG | W7NHAA | W912VG | MS NG | 7 | Non-Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
ARNG | A42 | MS MILITARY DEPT | National Guard | ARNG | W7NHAA | W35KT5 | MS NG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
ARNG | A37 | MS MILITARY DEPT | National Guard | ARNG | W7NHAA | W35KT6 | MS NG | 3 | Tactical | 2013-08-14 | 9 | 2013-02-15 | 2013-03-05 | 2013-04-16 | 2013-05-16 | 2013-06-14 | 2013-07-15
ASC | AF3 | USAG FT HOOD | Active - CONUS | ASC_W | W0VCAA | W81JFU | HOOD | 7 | Non-Tactical | 2013-10-09 | 10 | 2013-04-12 | 2013-04-30 | 2013-06-11 | 2013-07-11 | 2013-08-09 | 2013-09-09
ASC | WBP | DOL ISD S1 | Active - CONUS | ASC_W | W0VC01 | W45NQ7 | HOOD | 7 | Non-Tactical | 2013-10-09 | 10 | 2013-04-12 | 2013-04-30 | 2013-06-11 | 2013-07-11 | 2013-08-09 | 2013-09-09
ASC | WBR | COSCOM GS REPS2 | Active - CONUS | ASC_W | W0VC01 | W81MKE | HOOD | 7 | Non-Tactical | 2013-10-09 | 10 | 2013-04-12 | 2013-04-30 | 2013-06-11 | 2013-07-11 | 2013-08-09 | 2013-09-09
ASC | WBS | DOL ISD S1 | Active - CONUS | ASC_W | WOVCO1 | W81MKF | HOOD | 7 | Non-Tactical | 2013-10-09 | 10 | 2013-04-12 | 2013-04-30 | 2013-06-11 | 2013-07-11 | 2013-08-09 | 2013-09-09
FORSCOM | WJC | 115 BSB 1/1CD BCT | Active - CONUS | ASC_W | WH2DT0 | W45J67 | HOOD | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
FORSCOM | WJS | 215 BSB 3/1CD BCT | Active - CONUS | ASC_W | WH0KT0 | W81E1D | HOOD | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
FORSCOM | WJA | 15 BSB 2/1CD BCT | Active - CONUS | ASC_W | WH2ET0 | W45J66 | HOOD | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
FORSCOM | W48 | 509 FWD SPT CO | Active - CONUS | ASC_W | WCBWAA | W90ZTF | HOOD | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
FORSCOM | W0Z | A CO 589TH SB | Active - CONUS | ASC_W | WG07A0 | W91HC4 | HOOD | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
ARNG | A34 | USPFO WAREHOUSE SARS | National Guard | ARNG | W7NCAA | W81J63 | ME NG | 3 | Non-Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
ARNG | A38 | USPFO MA SARSS 1 MIL | National Guard | ARNG | W7NE02 | W13N92 | MA NG | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
ARNG | W69 | USPFO MA SARSS 1 DEV | National Guard | ARNG | W7NE02 | W13N93 | MA NG | 3 | Tactical | 2013-11-06 | 11 | 2013-05-10 | 2013-05-28 | 2013-07-09 | 2013-08-08 | 2013-09-06 | 2013-10-07
ASC | WJW | DOL AVN S1 | Active - CONUS | ASC_W | W0VC15 | W81F5M | HOOD | 3 | Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
ASC | WGX | DOL AVN S1 | Active - CONUS | ASC_W | W0VC15 | W81CL8 | HOOD | 3 | Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
FORSCOM | WGS | 615 ASB 1CD CAB | Active - CONUS | ASC_W | WJDZT0 | W4546G | HOOD | 3 | Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
USAREUR | WJ0 | OMA 21 SPO SSA | Active - OCONUS - E | USAREUR | WC0G02 | W91LEP | GERMANY | 3 | Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
USAREUR | WQD | RET SEC SSA | Active - OCONUS - E | USAREUR | WC0G02 | W80Q7B | GERMANY | 6 | Non-Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
USAREUR | WQE | RSA MAJOR ASSEMBLY | Active - OCONUS - E | USAREUR | WC0G02 | W800TM | GERMANY | 6 | Non-Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
USAREUR | WQF | RET CLIX SSA (SVC) | Active - OCONUS - E | USAREUR | WC0G02 | W803CR | GERMANY | 6 | Non-Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
USAREUR | AEQ | RSSA KAISERSLAUTERN | Active - OCONUS - E | USAREUR | W6FUA1 | WK4GBW | GERMANY | 3 | Tactical | 2013-12-04 | 12 | 2013-06-07 | 2013-06-25 | 2013-08-06 | 2013-09-05 | 2013-10-04 | 2013-11-04
ARNG | A73 | USPFO FOR FLORIDA | National Guard | ARNG | W7M2AA | W32RRX | FL NG | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
ARNG | A24 | USPFO FOR GEORGIA, G | National Guard | ARNG | W7M3AA | W81K57 | GA NG | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | ACM | RSSA BENELUX | Active - OCONUS - E | USAREUR | W6EZAA | WK3FQ3 | BELGIUM | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | WXA | 357 ADA CONOPS SSA | Active - OCONUS - E | USAREUR | WAXZAA | W9005D | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | ADW | 5/7 ADA SSA | Active - OCONUS - E | USAREUR | WHQCE0 | W80YWG | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | AMX | 240 QM CO SSA | Active - OCONUS - E | USAREUR | WE7P01 | WK4GDV | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | ACN | RSSA WACKENHEIM | Active - OCONUS - E | USAREUR | W6FUB5 | WK4F81 | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | A8M | USAREUR CONOPS | Active - OCONUS - E | USAREUR | W6N001 | WK4GEY | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | AF5 | RSSA MANNHEIM | Active - OCONUS - E | USAREUR | W6FUB4 | WK4GDD | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | AE5 | RSSA STUTTGART | Active - OCONUS - E | USAREUR | W6FUB8 | W811XN | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR/NETCOM | WQM | 5 SIG SSA | Active - OCONUS - E | USAREUR | W38C01 | W81PLH | GERMANY | 3 | Tactical | 2014-01-22 | 13 | 2013-07-26 | 2013-08-13 | 2013-09-24 | 2013-10-24 | 2013-11-22 | 2013-12-23
USAREUR | WYX | CJTF HOA SSA | Active - OCONUS - E | USAREUR | WJHEAA | W91K61 | DJIBOUTI | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | WXH | TF FALCON SSA | Active - OCONUS - E | USAREUR | W3VA9B | W90A0D | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | ACE | RSSA VICENZA | Active - OCONUS - E | USAREUR | W6E701 | W81AT1 | ITALY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | ACH | RSSA LIVORNO | Active - OCONUS - E | USAREUR | W6LFAA | W81AT0 | ITALY | 6 | Non-Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | ACW | 173 BSB SSA | Active - OCONUS - E | USAREUR | WARLAD | W81XT7 | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | WQ2 | 172 BSB SSA | Active - OCONUS - E | USAREUR | WJTPA0 | W90A0E | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | ACP | OMA LBE SSA | Active - OCONUS - E | USAREUR | W6FUA4 | W80S2V | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | WEA | 574 QM CO SSA | Active - OCONUS - E | USAREUR | WDCQ01 | W909PV | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | AEJ | RSSA VILSECK | Active - OCONUS - E | USAREUR | W1EK8A | WK4F8Q | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | WA3 | 2 SCR SSA | Active - OCONUS - E | USAREUR | WE35AD | W81X9C | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | WQ4 | 412 ASB SSA (KATT) | Active - OCONUS - E | USAREUR | WJERAA | WK4GF3 | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USAREUR | WRA | 412 ASB SSA (ILL) | Active - OCONUS - E | USAREUR | WJERA0 | WK4F8T | GERMANY | 3 | Tactical | 2014-02-19 | 14 | 2013-08-23 | 2013-09-10 | 2013-10-22 | 2013-11-21 | 2013-12-20 | 2014-01-20
USARPAC | WHJ | DOL SARSS1 | Active - OCONUS - W | USARPAC | W3RBAA | WX3JPR | HAWAII | 7 | Non-Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
USARPAC | WHQ | 536th MAINT/45 SUS | Active - OCONUS - W | USARPAC | WB25AA | W81B9W | HAWAII | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
USARPAC | W22 | 209 ASB 25 CAB | Active - OCONUS - W | USARPAC | WH9MA0 | WX3JJY | HAWAII | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
ARNG | A25 | USPFO FOR HI ARNG | National Guard | ARNG | W7M4AA | W81KK5 | HI NG | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
ARNG | W60 | 29 CSS BN | National Guard | ARNG | WYC7A0 | W80SW4 | HI NG | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
ASC | AW9 | DOL CL 2,4,7 | Active - CONUS | ASC_E | W0VA4B | W33NYN | STEWART | 7 | Non-Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
ASC | WFP | STK REC ACCT | Active - CONUS | ASC_E | W0VAAA | W33NYP | STEWART | 7 | Non-Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
FORSCOM | WFQ | 226 QM CO 87 CSSB | Active - CONUS | ASC_E | WDMJAA | W33RBS | STEWART | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
FORSCOM | WFE | 3 BSB 1/3ID BCT | Active - CONUS | ASC_E | WJATA0 | W81U3R | STEWART | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
FORSCOM | WFG | 26 BSB 2/3ID BCT | Active - CONUS | ASC_E | WJAUA0 | W81U3U | STEWART | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
FORSCOM | WFT | 603 ASB 3ID CAB | Active - CONUS | ASC_E | WJFKA0 | W33TLB | STEWART | 3 | Tactical | 2014-03-19 | 15 | 2013-09-20 | 2013-10-08 | 2013-11-19 | 2013-12-19 | 2014-01-17 | 2014-02-17
ASC | ADL | RBC_AIR AWCF SSA | Active - CONUS | ASC_E | W0U431 | W81XB3 | CAMPBELL | 7 | Non-Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
ASC | AW3 | DOL (GRND) DSU | Active - CONUS | ASC_E | W0U44B | W34XC5 | CAMPBELL | 7 | Non-Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WC7 | 563 ASB 159 CAB | Active - CONUS | ASC_E | WGNZA0 | W813LX | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WD5 | 96 ASB 101 CAB | Active - CONUS | ASC_E | WCBBA0 | W813LY | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WGA | 426 BSB 1/101 BCT | Active - CONUS | ASC_E | WACKA0 | W34XYK | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WGC | 626 BSB 3/101 BCT | Active - CONUS | ASC_E | WACFA0 | W34XYM | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WD8 | 305 CSSB | Active - CONUS | ASC_E | WE7RAA | W34GMT | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WFZ | 801 BSB 4/101 BCT | Active - CONUS | ASC_E | WACTA0 | W34TVH | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
FORSCOM | WGB | 526 BSB 2/101 BCT | Active - CONUS | ASC_E | WFJ3A0 | W34XYL | CAMPBELL | 3 | Tactical | 2014-04-16 | 16 | 2013-10-18 | 2013-11-05 | 2013-12-17 | 2014-01-16 | 2014-02-14 | 2014-03-17
USARPAC | WRB | 10 ASG OKINAWA | Active - OCONUS - W | USARPAC | W6CYA2 | WT6P5V | JAPAN | 7 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | WJX | 518 MNT CO PATRIOT | Active - OCONUS - W | USARPAC | WAC2E0 | W80Y3J | JAPAN | 3 | Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | WM5 | ISA SAGAMI ASL | Active - OCONUS - W | USARPAC | W6CYAA | WT5PV1 | JAPAN | 7 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | WM8 | OP PROJ SAGAMI | Active - OCONUS - W | USARPAC | W6CYAA | W81X7F | JAPAN | 7 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | AN4 | C CO 123RD | Active - OCONUS - W | USARPAC | WE2EAA | WC1JU3 | ALASKA | 3 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | AN7 | 98TH MAINT | Active - OCONUS - W | USARPAC | WEV8AA | W80Y69 | ALASKA | 3 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | WH0 | 725 BSB 4/25 BCT | Active - OCONUS - W | USARPAC | WC9TA0 | W91KGP | ALASKA | 3 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | WC3 | INSTLN SARSS | Active - OCONUS - W | USARPAC | W6L7AA | W80CWH | ALASKA | 7 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | WC4 | INSTLN SARSS | Active - OCONUS - W | USARPAC | 6RUAA1 | W80CWG | ALASKA | 7 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
USARPAC | AN6 | 25 BSB 1/25 SBCT | Active - OCONUS - W | USARPAC | WDPRA0 | WC1JU4 | ALASKA | 3 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
ARNG | A14 | USPFO FOR ALASKA | National Guard | ARNG | W7MUAA | W90DBX | AK NG | 3 | Non-Tactical | 2014-05-14 | 17 | 2013-11-15 | 2013-12-03 | 2014-01-14 | 2014-02-13 | 2014-03-14 | 2014-04-14
ASC | AY1 | INSTLN DBOF | Active - CONUS | ASC_W | W6CL06 | W45NSU | BLISS | 7 | Non-Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | WGT | 123 BSB 4/1AD BCT | Active - CONUS | ASC_W | WDJ6A0 | W4546F | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | W3K | 125 BSB 3/1AD BCT | Active - CONUS | ASC_W | WATGB2 | W918AR | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | AK2 | 5-52 AMD | Active - CONUS | ASC_W | WD0AF0 | W80FTD | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | AHQ | 1-43 ADA | Active - CONUS | ASC_W | WAWZF0 | W903FM | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | ANF | 501 BSB 1/1AD BCT | Active - CONUS | ASC_W | WH96A0 | WK4GAH | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | WGU | 127 ASB | Active - CONUS | ASC_W | WDSYAA | W91ED0 | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | WA8 | 2-43 ADA | Active - CONUS | ASC_W | WAWYE0 | W81THR | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
FORSCOM | W64 | 72 CS BN/212TH FiB | Active - CONUS | ASC_W | WB00AL | W8001Z | BLISS | 3 | Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
ASC | W15 | DOL WSMR | Active - CONUS | ASC_W | W6CJAA | W90TVF | WHITESANDS | 7 | Non-Tactical | 2014-06-11 | 18 | 2013-12-13 | 2013-12-31 | 2014-02-11 | 2014-03-13 | 2014-04-11 | 2014-05-12
ASC | BXN | DOL MAIN SITE | Active - CONUS | ASC_W | W0VN10 | W81RP6 | CARSON | 7 | Non-Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
ASC | WG2 | DOL RXA SITE | Active - CONUS | ASC_W | W0VN10 | W81RP5 | CARSON | 7 | Non-Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
ASC | WTU | ENVIRONMENTAL | Active - CONUS | ASC_W | W0VN10 | W90YP4 | CARSON | 3 | Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
FORSCOM | W9A | A CO 64 BSB | Active - CONUS | ASC_W | WJAXA0 | W51WKX | CARSON | 3 | Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
FORSCOM | W9C | 43ASG 183RD | Active - CONUS | ASC_W | WEVBAA | W80BTZ | CARSON | 3 | Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
FORSCOM | WJY | A CO 4 BSB | Active - CONUS | ASC_W | WJAYA0 | W81XF9 | CARSON | 3 | Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
MDW | ACZ | DOL-W | Active - CONUS | ASC_E | W06EAA | W74V77 | BELVOIR | 7 | Non-Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
MDW | ANY | FT BELVOIR S1 | Active - CONUS | ASC_E | W4VNAA | W810AG | BELVOIR | 7 | Non-Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
MDW | WXZ | 12 AVN BN SS | Active - CONUS | ASC_E | W0Y408 | W90YF4 | BELVOIR | 3 | Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
ASC | AY9 | FT LEONARD WOOD DOL | Active - CONUS | ASC_W | W6B810 | W58NQ5 | LEONARDWOOD | 7 | Non-Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
FORSCOM | W19 | 193 BSB 4 MEB | Active - CONUS | ASC_W | WJS5AA | W90UMS | LEONARDWOOD | 3 | Tactical | 2014-07-09 | 19 | 2014-01-10 | 2014-01-28 | 2014-03-11 | 2014-04-10 | 2014-05-09 | 2014-06-09
ARNG | A39 | USPFO FOR MICHIGAN | National Guard | ARNG | W7NFAA | W80X71 | MI NG | 3 | Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ARNG | A68 | USPFO FOR WEST VIRGI | National Guard | ARNG | W7N7AA | W81J6X | WV NG | 3 | Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ARNG | W55 | USPFO ACT WV ARNG | National Guard | ARNG | W7N7AA | W90EZX | WV NG | 7 | Non-Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ARNG | A51 | USPFO FOR NY SRA | National Guard | ARNG | W7NRAA | W16DDS | NY NG | 3 | Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ASC | AXT | US MIL ACAD S1 | Active - CONUS | ASC_E | W1FB08 | W16BCT | WESTPOINT | 7 | Non-Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ASC | WTZ | ABEERDEN PG S1 | Active - CONUS | ASC_E | W4QV01 | W90XN8 | APG | 7 | Non-Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ASC | AX2 | ISD MAINT | Active - CONUS | ASC_E | W1DCAA | W81EEL | DIX | 7 | Non-Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
FORSCOM | WFN | 703 BSB 4/3ID BCT | Active - CONUS | ASC_E | WDKAA0 | W33K09 | STEWART | 3 | Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ASC | AW4 | FT GORDON SARSS | Active - CONUS | ASC_E | W6CB23 | W33M8Q | GORDON | 7 | Non-Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ASC | AW5 | FT JACKSON S1 | Active - CONUS | ASC_E | W6CCAA | W37N01 | JACKSON | 7 | Non-Tactical | 2014-08-06 | 20 | 2014-02-07 | 2014-02-25 | 2014-04-08 | 2014-05-08 | 2014-06-06 | 2014-07-07
ARNG | W47 | CT AVCRAD SARSS-1 | National Guard | ARNG | W7TKAA | W90E3H | CT NG | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
ARNG | A19 | USPFO FOR CONNECTICU | National Guard | ARNG | W7MZ01 | W11M94 | CT NG | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
ARNG | W05 | W7MZ USPO ACTIVITY | National Guard | ARNG | W7TKAA | W912VJ | CT NG | 7 | Non-Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
ASC | AX8 | FT EUSTIS DOL | Active - CONUS | ASC_E | W6CNAA | W26RK4 | EUSTIS | 7 | Non-Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
FORSCOM | WKR | 1-7 ADA | Active - CONUS | ASC_E | WDQCA0 | W910DH | BRAGG | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
FORSCOM | WAN | ACO 407TH BN 2 BCT | Active - CONUS | ASC_E | WG6CA0 | W36LKH | BRAGG | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
FORSCOM | WF4 | F CO 4-5 AMD | Active - CONUS | ASC_W | WA1AF0 | W91E2E | HOOD | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
FORSCOM | W97 | 3 ACR | Active - CONUS | ASC_W | WEPNBD | W45RNQ | HOOD | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
FORSCOM | W58 | 1/62 ADA | Active-CONUS | ASC_W | WAXCE0 | W80000V | HOOD | 3 | Tactical | 2014-10-15 | 21 | 2014-04-18 | 2014-05-06 | 2014-06-17 | 2014-07-17 | 2014-08-15 | 2014-09-15
ASC | BXK | DOL SSA | Active - CONUS | ASC_W | W12KEK | W81UTH | LEWIS | 7 | Non-Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | W0S | 202 BSB 4/2SBCT | Active - CONUS | ASC_W | WC0CAD | W91HCZ | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | WNE | 308 BSB | Active - CONUS | ASC_W | WCBGAD | W90EU5 | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | WEL | 296 BSB 3/2SBCT | Active - CONUS | ASC_W | WE4QAD | W81TW6 | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | WEP | 542ND MAINT | Active - CONUS | ASC_W | WEXQAA | W68PPA | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | W63 | 607th FSC | Active - CONUS | ASC_E | WC7BAA | W8000Z | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | WGE | 402 BSB 5/2 SBCT | Active - CONUS | ASC_W | WJMSA0 | W90DY4 | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
FORSCOM | WD6 | G TRP 4/6 AVN |  | ASC_W | WC12FD | W34QWU | LEWIS | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16
USARC | WXT | AR-MEDCOM | Reserve | USARC | W858AA | W906CX | BRAGG | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
USARC | WXT | 3 MDSC | Reserve | USARC | W858AA | W906CX | BRAGG | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
USARC | WXT | 807 MDSC | Reserve | USARC | W858AA | W906CX | BRAGG | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
USARC | WTN | USACAPOC(A) | Reserve | USARC | WQW5HD | W90WYU | BRAGG | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
USARC | WY4 | 412 TEC | Reserve | USARC | WRXLAA | W906CN | BRAGG | 3 | Tactical | 2014-11-12 | 22 | 2014-05-16 | 2014-06-03 | 2014-07-15 | 2014-08-14 | 2014-09-12 | 2014-10-13
SDDC | A00 | MOTSU | Active - CONUS | ASC_E | W6TCAA | W8135W | SUNNYPOINT | 7 | Non-Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
ARNG | A33 | USPFO FOR LOUISIANA | National Guard | ARNG | W7NBAA | W42N6L | LA NG | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARSO | AY4 | CPBO FT SAM HOUSTON | Active - CONUS | ASC_W | W3VZ14 | W45NQP | SAMHOUSTON | 7 | Non-Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARPAC | W20 | 225 BSB 2/25 SBCT | Active - OCONUS - W | USARPAC | WH0GB0 | WX3V9P | HAWAII | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARPAC | W21 | 325 BSB 3/25ID D DSU | Active - OCONUS - W | USARPAC | WAL6B0 | WX3V9S | HAWAII | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARSO | W8V | USARSO SSA | OCONUS | USARSO | WJMW99 | W91EYF | SAMHOUSTON | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARSO | W46 | SPECIAL MISSIONS | OCONUS | USARSO | WJMYAH | W58EDN | SAMHOUSTON | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARSO | W59 | SOTO CANO AB | OCONUS | USARSO | W6BF01 | W90VTJ | HONDURAS | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARSO | WFA | JTF-BRAVO SSA | OCONUS | USARSO | W495AA | W8002F | HONDURAS | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
USARSO | WE0 | HHC 228 AV BNS1 | OCONUS | USARSO | WDX3T0 | W8080X | HONDURAS | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
ASC | XXXXXXXX | RUCKER SOUTH | Active - CONUS | ASC_E |  |  | EGLIN AFB | 3 | Tactical | 2014-12-03 | 23 | 2014-06-06 | 2014-06-24 | 2014-08-05 | 2014-09-04 | 2014-10-03 | 2014-11-03
ASC | AJ1 | OEF RETROGRADE | Active - CONUS | ASC_W | W46E7G | W91EKJ | SIERRA_AD | 7 | Non-Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | WWL | SIERRA ARMY DEPOT | Active - CONUS | ASC_W | W0GWAA | W90762 | SIERRA_AD | 7 | Non-Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
NETCOM | AXQ | CSSF 1110TH SIG | Active - CONUS | ASC_E | WHBWAA | W23P47 | DETRICK | 7 | Non-Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
USARC | ABC | 103 ESC | Reserve | USARC | WSPQAA | W81Y1M | BRAGG | 3 | Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
USARC | WEN | 1011 CS CO S1 | Reserve | USARC | WQ58A1 | W81NNG | BRAGG | 3 | Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | W57 | YUMA DOL | Active-CONUS | ASC_W | W6CKAA | W8000S | YUMA PG | 7 | Non-Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | W34 | REDSTONE ISSA | Active - CONUS | ASC_E | W0WFAA | W5J9KB | REDSTONE | 7 | Non-Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | WB0 | OEF TRNG BDE | Reserve | USARC | W3NQ03 | W919TW | ATTERBURY | 3 | Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | WG0 | DET 25 | Reserve | USARC | W3NQ06 | W91KAA | SHELBY | 3 | Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ARNG | A16 | USPFO ARKANSAS | National Guard | ARNG | W7MWAA | W81K14 | AR NG | 3 | Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | WGQ | DET 25 | Reserve | USARC | W3NQ05 | W91J8E | SHELBY | 3 | Tactical | 2015-01-21 | 24 | 2014-07-25 | 2014-08-12 | 2014-09-23 | 2014-10-23 | 2014-11-21 | 2014-12-22
ASC | AXB | FT KNOX SARSS1 | Active - CONUS | ASC_E | W6CD04 | W22PEQ | KNOX | 7 | Non-Tactical | 2015-02-18 | 25 | 2014-08-22 | 2014-09-09 | 2014-10-21 | 2014-11-20 | 2014-12-19 | 2015-01-19
FORSCOM | WQZ | 201 BSB 3/1ID BCT | Active - CONUS | ASC_E | WH51AS | WK4GD0 | KNOX | 3 | Tactical | 2015-02-18 | 25 | 2014-08-22 | 2014-09-09 | 2014-10-21 | 2014-11-20 | 2014-12-19 | 2015-01-19
ASC | AW1 | DOL | Active - CONUS | ASC_E | W6CR54 | W33BQ9 | BENNING | 7 | Non-Tactical | 2015-03-18 | 26 | 2014-09-19 | 2014-10-07 | 2014-11-18 | 2014-12-18 | 2015-01-16 | 2015-02-16
FORSCOM | W72 | 598TH MAINT CO | Active - CONUS | ASC_E | WE7MAA | W81PPN | BENNING | 3 | Tactical | 2015-03-18 | 26 | 2014-09-19 | 2014-10-07 | 2014-11-18 | 2014-12-18 | 2015-01-16 | 2015-02-16
FORSCOM | WFM | 203 BSB 3/3ID BCT | Active - CONUS | ASC_E | WJD2A0 | W33JWH | BENNING | 3 | Tactical | 2015-03-18 | 26 | 2014-09-19 | 2014-10-07 | 2014-11-18 | 2014-12-18 | 2015-01-16 | 2015-02-16
FORSCOM | WXB | 3-4 ADA | Active - CONUS | ASC_E | WH1ZAA | W900JH | BRAGG | 3 | Tactical | 2015-03-18 | 26 | 2014-09-19 | 2014-10-07 | 2014-11-18 | 2014-12-18 | 2015-01-16 | 2015-02-16
FORSCOM | WAL | BCO 782D BSB 4 BCT | Active - CONUS | ASC_E | WABYAD | W36N0V | BRAGG | 3 | Tactical | 2015-03-18 | 26 | 2014-09-19 | 2014-10-07 | 2014-11-18 | 2014-12-18 | 2015-01-16 | 2015-02-16
FORSCOM | W33 | 29TH FWD SPT CO | Active - CONUS | ASC_E | WH1MAA | W5J9M5 | BRAGG | 3 | Tactical | 2015-03-18 | 26 | 2014-09-19 | 2014-10-07 | 2014-11-18 | 2014-12-18 | 2015-01-16 | 2015-02-16
ASC | AY5 | DOL | Active - CONUS | ASC_W | W6CS4B | W44DQ1 | SILL | 7 | Non-Tactical | 2015-04-15 | 27 | 2014-10-17 | 2014-11-04 | 2014-12-16 | 2015-01-15 | 2015-02-13 | 2015-03-16
FORSCOM | WRJ | 168 MAINT CO | Active - CONUS | ASC_W | WDG5A0 | W44KN3 | SILL | 3 | Tactical | 2015-04-15 | 27 | 2014-10-17 | 2014-11-04 | 2014-12-16 | 2015-01-15 | 2015-02-13 | 2015-03-16
FORSCOM | WRK | 100 MAINT CO | Active - CONUS | ASC_W | WDQCA0 | WK4GAA | SILL | 3 | Tactical | 2015-04-15 | 27 | 2014-10-17 | 2014-11-04 | 2014-12-16 | 2015-01-15 | 2015-02-13 | 2015-03-16
FORSCOM | W51 | 4-3 ADA | Active - CONUS | ASC_W | WH12E0 | W8000Q | SILL | 3 | Tactical | 2015-04-15 | 27 | 2014-10-17 | 2014-11-04 | 2014-12-16 | 2015-01-15 | 2015-02-13 | 2015-03-16
FORSCOM | ADK | 3-2 ADA | Active - CONUS | ASC_W | WHU9E0 | W81NMJ | SILL | 3 | Tactical | 2015-04-15 | 27 | 2014-10-17 | 2014-11-04 | 2014-12-16 | 2015-01-15 | 2015-02-13 | 2015-03-16
ARNG | A27 | ILLINOIS ARMY NATION | National Guard | ARNG | W7M6AA | W81JTY | IL NG | 3 | Tactical | 2015-04-15 | 27 | 2014-10-17 | 2014-11-04 | 2014-12-16 | 2015-01-15 | 2015-02-13 | 2015-03-16
USARC | WXX | 143RD USARC SARSS1 | Reserve | USARC | WNBURH | W906CT | BRAGG | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
USARC | WXX | 377 TSC | Reserve | USARC | WNBURH | W906CT | BRAGG | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
USARC | WXX | DSC | Reserve | USARC | WNBURH | W906CT | BRAGG | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
USARC | WXX | 316 ESC | Reserve | USARC | WNBURH | W906CT | BRAGG | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
FORSCOM | WGW | 27 BSB 4/1CD | Active - CONUS | ASC_W | WDJ9A0 | W42SU8 | HOOD | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
FORSCOM | WHX | 62 QM CO | Active - CONUS | ASC_W | WEYNAA | W80XYJ | HOOD | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
ARNG | A28 | USPFO FOR INDIANA | National Guard | ARNG | W7M7AA | W81JR8 | IN NG | 3 | Tactical | 2015-05-13 | 28 | 2014-11-14 | 2014-12-02 | 2015-01-13 | 2015-02-12 | 2015-03-13 | 2015-04-13
ASC | AX4 | DRUM DOL | Active - CONUS | ASC_E | W0XQ4U | W81W29 | DRUM | 7 | Non-Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
FORSCOM | WHA | 277TH CS BN | Active - CONUS | ASC_E | WDMGB0 | W81C01 | DRUM | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
FORSCOM | WHC | 514TH MAINT CO | Active - CONUS | ASC_E | WHLKAA | W810DR | DRUM | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
FORSCOM | WHH | B CO 210TH FSB | Active - CONUS | ASC_E | WD80AA | W90ADT | DRUM | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
FORSCOM | WHE | A CO 10 BSB | Active - CONUS | ASC_E | WD82AA | W90ADP | DRUM | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
FORSCOM | WG9 | B CO 710TH | Active - CONUS | ASC_E | WEPGAA | W81ALT | DRUM | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
ARNG | A54 | USPFO STORAGE AND DI | National Guard | ARNG | W7NU01 | W24L9M | OH NG | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
ARNG | A57 | USPFO FOR PENNSYLVAN | National Guard | ARNG | W7NXAA | W25KYQ | PA NG | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
ARNG | AVE | USFPO PENNSYLVANIA S | National Guard | ARNG | W7NXAA | W91AAK | PA NG | 7 | Non-Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
ARNG | WCY | COMPANY C 728TH MSB | National Guard | ARNG | W7NXAA | W8071K | PA NG | 3 | Tactical | 2015-06-10 | 29 | 2014-12-12 | 2014-12-30 | 2015-02-10 | 2015-03-12 | 2015-04-10 | 2015-05-11
USARC | WMG | 200 MP CMD | Reserve | USARC | WS65AA | W806BY | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
USARC | WMG | 79 SSC | Reserve | USARC | WS65AA | W806BY | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
USARC | WMG | 4 ESC | Reserve | USARC | WS65AA | W806BY | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
USARC | WMG | 364 ESC | Reserve | USARC | WS65AA | W806BY | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
USARC | WMG | 311 ESC | Reserve | USARC | WS65AA | W806BY | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
USARC | WMG | 451 ESC | Reserve | USARC | WS65AA | W806BY | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
USARC | WY3 | 11 AVN RGT | Reserve | USARC | WZ3NA0 | W906CP | OGDEN | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
ASC | AY8 | DBOF SARSS1 | Active - CONUS | ASC_W | W0VM72 | W90A84 | RILEY | 7 | Non-Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
ASC | WCQ | DOL GS/RX | Active - CONUS | ASC_W | W0VM68 | W90A87 | RILEY | 7 | Non-Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
FORSCOM | WJP | 101 BSB 1/1ID BCT | Active - CONUS | ASC_W | WJA1A0 | W81WRD | RILEY | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
FORSCOM | WJQ | 299 BSB 2/1ID BCT | Active - CONUS | ASC_W | WH87A0 | W81WRE | RILEY | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
FORSCOM | WW0 | 610 BSB 4/1ID | Active - CONUS | ASC_W | WDMWA0 | W91ZLD | RILEY | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
FORSCOM | WQT | 601 ASB 1ID CAB | Active - CONUS | ASC_W | WJEQA0 | WK4BNX | RILEY | 3 | Tactical | 2015-07-13 | 30 | 2015-01-14 | 2015-02-03 | 2015-03-13 | 2015-04-14 | 2015-05-14 | 2015-06-12
FORSCOM | W8H | A CO 404TH ASB | ASC_W | ASC_W | WJYCA0 | W33R7X | CARSON | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
FORSCOM | WJN | A CO 204 BSB | Active - CONUS | ASC_W | WJAZA0 | W81XGA | CARSON | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
FORSCOM | WCH | A CO 704 BSB | Active - CONUS | ASC_W | WAJEA0 | W81U1J | CARSON | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
FORSCOM | W7B | 1-44 AMD | Active - CONUS | ASC_W | WD21F0 | W91TB4 | HOOD | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
FORSCOM | W81 | W6DK MISSION SUPPORT DET 41 | ASC_W | ASC_W | W6DKX8 | W9177E | HOOD | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
ARNG | A41 | DOL-WAREHOUSE | National Guard | ARNG | W7NGAA | W57LVB | MN NG | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
ARNG | A69 | USPFO FOR WISCONSIN- | National Guard | ARNG | W7N801 | W5CK4Y | WI NG | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
USARC | WSM | 416TH TEC | Reserve | USARC | WRXMAA | W8134B | OGDEN | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
USARC | WSQ | MIRC | Reserve | USARC | WQW6A4 | W8134B | OGDEN | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
USARC | WSQ | USARJSTSC | Reserve | USARC | WQW6A4 | W8134B | OGDEN | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
FORSCOM | W66 | F CO 58 AVN DS | Active - CONUS | ASC_E | WJEVAA | W80KG6 | RUCKER | 3 | Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
ASC | AW8 | DOL | Active - CONUS | ASC_E | W6CEAA | W31NWR | RUCKER | 7 | Non-Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
TRADOC | W0H | A CO 1-210 AVN | Active - CONUS | ASC_E | WOU91Y | W31NWY | RUCKER | 7 | Non-Tactical | 2015-08-12 | 31 | 2015-02-13 | 2015-03-03 | 2015-04-14 | 2015-05-14 | 2015-06-12 | 2015-07-13
ASC | AZY | DOL SARSS1 | Active - CONUS | ASC_W | W6CFAA | W61DEV | HUACHUCA | 7 | Non-Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ASC | AY7 | LEAVENWORTH S1 | Active - CONUS | ASC_W | W0VP06 | W55NS0 | LVNWORTH | 7 | Non-Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ASC | WA7 | DOL IMMD SARSS1 | Active - CONUS | ASC_E | W0VF4M | W81TTH | POLK | 7 | Non-Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ASC | AY3 | CPBO FORT POLK | Active - CONUS | ASC_E | W0VF4M | W8115U | POLK | 7 | Non-Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
FORSCOM | W03 | 88 BDB 1 MEB | Active - CONUS | ASC_E | WC27A0 | W90M5S | POLK | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
FORSCOM | W2B | 6/353 IN RGT | Active - CONUS | ASC_E | WCA9B0 | W90Z3J | POLK | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
USARC | W87 | 81 RSC | Reserve | USARC | WQ7TAA | W809JG | POLK | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
FORSCOM | WBJ | ACO 94TH BSB | Active - CONUS | ASC_E | WCA9B0 | W68RZ2 | POLK | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ARNG | A09 | USPFO KS ARNG | National Guard | ARNG | W7M9AA | W908G3 | KS NG | 7 | Non-Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ARNG | A31 | USPFO FOR KANSAS WAR | National Guard | ARNG | W7M9AA | W81K4N | KS NG | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ARNG | A11 | USPFO WAREHOUSE DCSL | National Guard | ARNG | W7NOAA | W81LBJ | SD NG | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ARNG | A53 | DCSLOG WAREHOUSE | National Guard | ARNG | W7NTAA | W81J62 | ND NG | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
ARNG | A45 | USPFO WHS ACT ABF ST | National Guard | ARNG | W7NL01 | W59TYJ | NE NG | 3 | Tactical | 2015-10-14 | 32 | 2015-04-17 | 2015-05-05 | 2015-06-16 | 2015-07-16 | 2015-08-14 | 2015-09-14
USARPAC | WET | MSC-K CLII/IX GR | Active - OCONUS - W | USARPAC | W0C3AA | W90DGU | KOREA | 7 | Non-Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | WLX | MSC-K CLIII/IV | Active - OCONUS - W | USARPAC | W397AA | W90DGX | KOREA | 7 | Non-Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | WCC | 302ND BSB | Active - OCONUS - W | USARPAC | WAJDA0 | W81U1K | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | AKS | 602ND ASB | Active - OCONUS - W | USARPAC | WJGSA0 | WT4KD8 | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | AG9 | 520 MAINT CO | Active - OCONUS - W | USARPAC | WCBR02 | WT4KDK | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | WER | 178TH MAINT (PAT) | Active - OCONUS - W | USARPAC | WH19E0 | W808M9 | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC/NETPAC | WM9 | 1ST SIG BDE | Active - OCONUS - W | USARPAC | WDMAAA | WT4G36 | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | AKC | 595TH MAINT (SP 51) | Active - OCONUS - W | USARPAC | WE7K01 | WT4KDR | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | AKN | 61 MAINT CO | Active - OCONUS - W | USARPAC | WB4J01 | WT4KDV | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | AKT | 498TH CSSB (SP 60) | Active - OCONUS - W | USARPAC | WCBKAA | WT4KEA | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
USARPAC | AKX | 3D MAINT (PAT) | Active - OCONUS - W | USARPAC | WAW0F0 | W81X30 | KOREA | 3 | Tactical | 2015-11-11 | 33 | 2015-05-15 | 2015-06-02 | 2015-07-14 | 2015-08-13 | 2015-09-11 | 2015-10-12
ARNG | A55 | USPFO FOR OKLAHOMA | National Guard | ARNG | W7NVAA | W81L6Y | OK NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A63 | USPFO FOR TEXAS WHS | National Guard | ARNG | W7N201 | W81JTH | TX NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A43 | WAREHOUSE USPFO-MO | National Guard | ARNG | W7NJAA | W58MYQ | MO NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A79 | 1107TH AVCRAD SRA | National Guard | ARNG | W7TLAA | W81PNC | MO NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | W04 | W7NJ USPO ACTIVITY | National Guard | ARNG | W7NJAA | W912VK | MO NG | 7 | Non-Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
USARC | W14 | 63RSC S1 | Reserve | USARC | W0F4AA | W90DAN | OGDEN | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A18 | USPFO-CO | National Guard | ARNG | W7MYAA | W81LJT | CO NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | WYF | USPFO FOR COLORADO S | National Guard | ARNG | W7MYAA | W91CUH | CO NG | 7 | Non-Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A71 | USPFO FOR WYOMING SR | National Guard | ARNG | W7N9AA | W5DK52 | WY NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A44 | USPFO FOR MONTANA | National Guard | ARNG | W7NK01 | W81JKX | MT NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A49 | USPFO-WAREHOUSE | National Guard | ARNG | W7NQAA | W43MYP | NM NG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
USARC | WTH | 99TH RSC S1 | Reserve | USARC | WQZZA1 | W90NHW | CHAMBERSBURG | 3 | Tactical | 2015-12-02 | 34 | 2015-06-05 | 2015-06-23 | 2015-08-04 | 2015-09-03 | 2015-10-02 | 2015-11-02
ARNG | A26 | USPFO WHSE FOR ID | National Guard | ARNG | W7M5AA | W81H2P | ID NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | WK5 | CLASS IX SSA | National Guard | ARNG | WTQ2A2 | W81H0W | ID NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | A47 | USPFO FOR NEVADA SAR | National Guard | ARNG | W7NMAA | W81H7U | NV NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | A64 | SREW7N3 USPFO ACTIVI | National Guard | ARNG | W7N3AA | W81KK3 | UT NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
USARC | WSK | 88TH RSC S1 | Reserve | USARC | W6KGAA | W57KFP | MCCOY | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
USARC | AYF | SSD MC DBOF S1 | Reserve | USARC | W0XY38 | W5CD3D | MCCOY | 7 | Non-Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | A15 | USPFO FOR ARIZONA | National Guard | ARNG | W8AW08 | W61LQA | AZ NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | A58 | USPFO FOR PUERTO RIC | National Guard | ARNG | W7PAAA | W81K59 | PR NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | A67 | USPFO FOR WASHINGTON | National Guard | ARNG | W7N6AA | W68KCW | WA NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | WDF | YASL 181ST CS BN SAR | National Guard | ARNG | WQYTAA | W68NES | WA NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | A56 | DOL-S&S WAREHOUSE SA | National Guard | ARNG | W7NWAA | W66MRR | OR NG | 3 | Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
ARNG | WWN | USPO OREGON SARSS1 | National Guard | ARNG | W7N2AA | W90AJG | OR NG | 7 | Non-Tactical | 2016-01-20 | 35 | 2015-07-24 | 2015-08-11 | 2015-09-22 | 2015-10-22 | 2015-11-20 | 2015-12-21
USARC | WME | 1ST MSC S1 | Reserve | USARC | W1H1AA | W800FE | 1ST_MSC | 7 | Non-Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | A17 | USPFO FOR CALIFORNIA | National Guard | ARNG | W7MXAA | W81LG6 | CA NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | A76 | AVCRAD | National Guard | ARNG | W7TMHD | W81PL2 | CA NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | W0D | CAARNG AVCRAD | National Guard | ARNG | W7MXAA | W912VH | CA NG | 7 | Non-Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | W79 | SARSS 1 ACTIVITY #2 | National Guard | ARNG | W7MXAA | W80H45 | CA NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | WDA | SARSS1 CLASS IX ACTI | National Guard | ARNG | W7MXAA | W808GP | CA NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | A22 | USPFO-DC ARMY NATION | National Guard | ARNG | W71MAA | W81KJK | DC NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
FORSCOM | WDP | ROTATION GOLD | Active - CONUS | ASC_W | W6F7ST | W80TAW | IRWIN | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ASC | AMR | USAG FT IRWIN | Active - CONUS | ASC_W | W4E6AA | W80WKN | IRWIN | 7 | Non-Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
FORSCOM | WDK | NTC DSSA (ITT) | Active - CONUS | ASC_W | W6F764 | W80QJK | IRWIN | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
FORSCOM | WDN | ROTATION BLUE | Active - CONUS | ASC_W | W6F7SP | W81HM6 | IRWIN | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | A75 | USPFO-GU WAREHOUSE S | National Guard | ARNG | W7QPAA | W80GYB | GU NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARNG | A72 | USP&FO WAREHOUSE | National Guard | ARNG | W7RQAA | WF3APY | VI NG | 3 | Tactical | 2016-02-17 | 36 | 2015-08-21 | 2015-09-08 | 2015-10-20 | 2015-11-19 | 2015-12-18 | 2016-01-18
ARCENT | WJ3 | 5-52 ADA PATRIOT BH | AOR | ARCENT | WJN241 | W912BX | BAHRAIN | 3 | Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | WN9 | 1-43 ADA | AOR | ARCENT | WATGAD | W91PPJ | QATAR | 3 | Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W1H | 5-52 ADA PATRIOT UAE | AOR | ARCENT | WJN221 | W90V9R | UAE | 3 | Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | WAV | MFO | AOR | ARCENT | W4JQAA | W81CJK | EGYPT | 7 | Non-Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W8C | QATAR MULTI-COMMODIT | AOR | ARCENT | WATGE5 | W91DXY | QATAR | 7 | Non-Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W2N | GS SRA RET ARIFJAN | AOR | ARCENT | WATGF2 | W91P9H | KUWAIT | 7 | Non-Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W2Q | GS CLASS IX-AIR | AOR | ARCENT | WATGF3 | W91PAM | KUWAIT | 7 | Non-Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W37 | SRA PATRIOT ARIFJAN | AOR | ARCENT | W47TA6 | W5J9V5 | KUWAIT | 3 | Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W7A | GS SRA ARIFJAN | AOR | ARCENT | WATGC2 | W91QSU | KUWAIT | 7 | Non-Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | W7Z | DS SRA ARIFJAN | AOR | ARCENT | WATGF5 | W91RH2 | KUWAIT | 3 | Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
ARCENT | WKQ | DS SRA BUEHRING | AOR | ARCENT | WATGF4 | W910M2 | KUWAIT | 3 | Tactical | 2016-03-15 | 37 | 2015-09-17 | 2015-10-06 | 2015-11-16 | 2015-12-16 | 2016-01-15 | 2016-02-12
SOCOM | W68 | US SOCOM | Active-CONUS | ASC_E |  |  | MCDILL AFB | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USASOC | WP0 | 3D SFG GSB | Active - CONUS | ASC_E | WHQLA9 | W91KBP | BRAGG | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USASOC | WR0 | 10 SFG GSB | Active - CONUS | ASC_E | WDSPA9 | W91M23 | CARSON | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USASOC | WQ0 | 7 SFG GSB | Active - CONUS | ASC_E | WDSNA9 | W91KBQ | EGLIN AFB | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USASOC | WD7 | 160TH SOAR | Active - CONUS | ASC_E | WDSTAA | W80N5C | CAMPBELL | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USASOC | WN0 | 5 SFG GSB | Active - CONUS | ASC_E | WDSMA9 | W91LCR | CAMPBELL | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USASOC | WM0 | 1 SFG GSB | Active - CONUS | ASC_E | WDSLB0 | W91M1Z | LEWIS | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
FORSCOM | WAP | ACO 82D BSB 3 BCT | Active - CONUS | ASC_E | WG6CA0 | W36LKJ | BRAGG | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USAREUR | WQ9 | 170 BSB SSA | Active - OCONUS - E | USAREUR | [5 empty] | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USAREUR | WQ3 | HHBN USAREUR | Active - OCONUS - E | USAREUR | WATLYA | WK4GEY | GERMANY | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USAREUR | WB3 | MAINT ACT PERM SSA | Active - OCONUS - E | USAREUR | WC0G02 | W80N6Y | GERMANY | 6 | Non-Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USAREUR | AG2 | Class IX SSA AQCF | Active - OCONUS - E | USAREUR | W6FUA3 | W90AGJ | GERMANY | 6 | Non-Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USAREUR | WB2 | RET CLII/CLIV SSA | Active - OCONUS - E | USAREUR | WC0G02 | WK4EYJ | GERMANY | 6 | Non-Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USAREUR | WQP | TASA SSA | Active - OCONUS - E | USAREUR | W0H93A | WK4GFY | GERMANY | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARNG | W80 | NATIONAL GUARD MATER | National Guard | ARNG | W7NAAA | W90JFF | KY NG | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARNG | AV6 | USPFO IOWA SSF SARSS | National Guard | ARNG | W7M8AA | W91AAM | IA NG | 7 | Non-Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | A4X | JSSC JPO MRAP SSA | AOR | ARCENT | W4GG4Q | W5J9DM | AFGHANISTAN | 7 | Non-Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W0F | SALERNO AVN | AOR | ARCENT | WATGC7 | W81T8T | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W0P | FOB SHARANA MULTI | AOR | ARCENT | WATGC7 | W91GLW | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W1P | FOB SHANK MULTI | AOR | ARCENT | WJN261 | W90VPT | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W28 | TF PHOENIX | AOR | ARCENT | WJN262 | W90Y0S | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W29 | FOB LNK MULTI CLASS | AOR | ARCENT | WJN267 | W90Z0G | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W2A | FOB TK MULTI AVN | AOR | ARCENT | WJN266 | W90Z2Z | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W2C | MAZAR-E-SHARIF MULTI | AOR | ARCENT | WATGB8 | W91YWB | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W2W | FOB FENTY MULTI | AOR | ARCENT | WATGBH | W91PFK | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W2Z | MAZAR-E-SHARIF AVN | AOR | ARCENT | WATGE3 | W91YSX | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W36 | KAF MULTI STRYKER | AOR | ARCENT | WJN269 | W5J9T0 | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W45 | SHINDAND MULTI AVN | AOR | ARCENT | WJN26A | W5K9JQ | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W53 | FOB WALTON MULTI | AOR | ARCENT | WJN25E | W56APX | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W8D | KAF MULTI CLASS | AOR | ARCENT | WATGD3 | W91DX3 | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W8E | KAF MULTI AVN | AOR | ARCENT | WATGC6 | W91DY0 | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W8G | BAF MULTI CLASS | AOR | ARCENT | WATGD2 | W91EB8 | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | W9Z | BAF AVN | AOR | ARCENT | WATGD5 | W91RN4 | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | WJE | FOB WILSON MULTI | AOR | ARCENT | WATGF9 | W9117P | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
ARCENT | WKW | TF 373 SOC BAGRAM | AOR | ARCENT | WATGD8 | W9118J | AFGHANISTAN | 3 | Tactical | TBD | TBD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
D-180 = IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-180)=1,[FIELDING (BLACKOUT DATE)]-182,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-180)=7,[FIELDING (BLACKOUT DATE)]-181,[FIELDING (BLACKOUT DATE)]-180))
Adv LU Trg - (D-160) = IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-160)=1,[FIELDING (BLACKOUT DATE)]-165,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-160)=2,[FIELDING (BLACKOUT DATE)]-166,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-160)=4,[FIELDING (BLACKOUT DATE)]-161,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-160)=5,[FIELDING (BLACKOUT DATE)]-162,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-160)=6,[FIELDING (BLACKOUT DATE)]-163,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-160)=7,[FIELDING (BLACKOUT DATE)]-164, [FIELDING (BLACKOUT DATE)]-160))))))
D-120 = IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-120)=1,[FIELDING (BLACKOUT DATE)]-122,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-120)=7,[FIELDING (BLACKOUT DATE)]-121,[FIELDING (BLACKOUT DATE)]-120))
D-90 = IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-90)=1,[FIELDING (BLACKOUT DATE)]-92,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-90)=7,[FIELDING (BLACKOUT DATE)]-91,[FIELDING (BLACKOUT DATE)]-90))
D-60 = IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-60)=1,[FIELDING (BLACKOUT DATE)]-62,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-60)=7,[FIELDING (BLACKOUT DATE)]-61,[FIELDING (BLACKOUT DATE)]-60))
D-30 = IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-30)=1,[FIELDING (BLACKOUT DATE)]-32,IF(WEEKDAY([FIELDING (BLACKOUT DATE)]-30)=7,[FIELDING (BLACKOUT DATE)]-31,[FIELDING (BLACKOUT DATE)]-30))